December 22, 2005

AmerenUE

Rhonda Bartram

1901 Chouteau Avenue

P.O. Box 66149, MC 700

St. Louis, MO 63166-6149

Dear Rhonda:

Your plans and actual cost estimate for your overhead electric relocation has been approved for MoDOT job number J3P0596C, for the Highways 61 and C interchange at Moscow Mills in Lincoln County.   Please prepare your Actual Cost Reimbursable Utility Relocation Agreement for this project.  This relocation has been found to be reimbursable by MoDOT in the sum of $633,953.90.  Actual Cost payment for this relocation will be paid once the agreement has been executed.

Ameren is charging 40% of the actual materials used as “minor Materials” charge for a total cost of $85,972.00.  This cost will need to be substantiated in the final bill.

The estimate included “Miscellaneous Construction Expenditures” charges totaling $28,415.60.  Ameren stated these are indirect overhead charges, and provided no support or detailed estimate for these charges.  Ameren will need to provide documentation of these charges on its final invoice.

It is our understanding that the boring and tree trimming will be performed under continuing contract.  Continuing contracts must be provided to support the costs at the time of audit.  Ameren is required to keep detailed documentation showing the materials used, detailed invoices for hours charged, and invoices for any outside work charged to the project.  In addition, documentation for the above mentioned costs and all additives and overheads will be required during audit.  Failure to maintain this documentation could result in questioned costs.

You are authorized to proceed with your relocation with Ameren forces.  This job is currently scheduled for a February 2006 letting, and your relocation work should be completed by May 1, 2006.  All right of way has been acquired for your relocation, demolition should take place around the middle of February.  Please proceed at your earliest convenience and once Jack Sullivan, South Area Permit Specialist, has issued a permit.

Contact Mark Croarkin at the Troy Project Office 5 days prior to beginning any construction activities at (636) 528-3169.  Please make every effort to keep him informed of your progress and schedule.  If you have any questions or concerns, please contact me at (573) 248-2602, or michael.baxter@modot.mo.gov.

Sincerely,

Michael E. Baxter, P.E.

District Utilities Engineer

copy:	Chuck Twellmann, AmerenUE

Ken Warbritton P.E., District Construction

Mark Croarkin, P.E., Resident Engineer

Dave Ahlvers, P.E., State Construction Engr.

Patti Holzem, Controllers Office

Jack Sullivan, South Area Permit Specialist