Key Environmental/Cultural Resources Compliance Milestones

| Task/Submittal | LPA Responsibility | MoDOT Responsibility | Timeframe |
| --- | --- | --- | --- |
| Obtain NEPA classification | Provide adequate project information with Request for Environmental Review | Provide classification | 30 days |
| Complete NEPA documentation if required: 1. Programmatic CE (no documentation required) 2. Letter CE 3. CE2 4. EA 5. EIS | Prepare and submit required documentation | Review documentation, provide comments, and submit documentation (revised by LPA as needed) to FHWA | 1. Programmatic CE– 4 weeks 2. Letter CE–6 weeks 3. CE2–10 weeks 4. EA–18 months 5. EIS–36 months |
| Comply with Section 106 (cultural resources) | Obtain SHPO's concurrence | Ensure Section 106 compliance | Generally 10 weeks *Can take 6–12 months if SHPO finds adverse effect |
| Section 4 (f) 1. Historic bridge programmatic 2. Public land prog. or de minimis 3. Full draft and final evaluation | 1. Prepare MOA 2. Provide documentation 3. Provide documentation | 1. Review MOA 2. Review & submit to FHWA 3. Review & submit to FHWA | 1. 6 months 2. 60 days 3. 12 months |
| Comply with Clean Water Act Sections 404 and 401 | Obtain permits | Ensure compliance | Nationwide: 6–8 weeks Individual: 4–6 months |
| Comply with Endangered Species Act | Consult with MDC and obtain clearance letter | Review consultation | 1–6 months |
| Floodplains | Contact local floodplain administrator for any needed permits | Ensure compliance | 1–6 months |
| Comply with Clean Water Act Section 602 | Obtain NPDES permit | Ensure Section 602 compliance | 1–3 months |
| Comply with env. laws regarding use of borrow & spoil sites | Comply with applicable laws | Ensure compliance with applicable laws | Varies according to law |
| Hazardous waste | Determine presence, contact DNR if hazardous materials are found | Ensure compliance | 1 month |
| Comply with Farmland Protection Policy Act (FPPA) | Obtain Farmland Rating | Ensure FPPA compliance | 6 weeks |
| Environmental Justice, Title VI, ADA, etc. | Ensure compliance | Ensure compliance | 1 month |
| Noise | Complete noise study if necessary | Ensure compliance | 1–6 months |
| Comply with Clean Air Act | Ensure Clean Air Act compliance, model if necessary | Ensure Clean Air Act compliance | 6–12 months if modeling required |