County

Route

Job Number

(New 1-1-03)

# Core Team Member

## PROJECT DEVELOPMENT LIAISON

## SCOPING CHECKLIST

(Add additional notes as required)

A project’s scope can be defined as the set of design parameters that precisely satisfy the purpose and need of the project. A poorly identified scope that is broader than the purpose and need will result in an unnecessarily high project budget and schedule, while a scope which falls short will yield a project that accomplishes little of significance.   While an accurate project scope is difficult to identify early in development, a careful, multidisciplinary examination of the purpose and need will produce a solid foundation upon which project development can occur.

This checklist is designed to stimulate thought on those project parameters that are sometimes overlooked and whose omission can jeopardize the integrity of the scope.   At the initial scoping meeting, the appropriate core team member should fill out the checklist as completely as possible.  As project development progresses, the core team member should continue to update the checklist and coordinate with the project manager.  In this manner, potential changes to the project scope can be dealt with as they emerge and the scope represented by the preliminary plan will be as accurate as possible.

|  | Review NEPA document (ROD, FONSI, etc.) to ensure any commitments or mitigation efforts are included in the scope. |
| --- | --- |
|  | Determine appropriate level of FHWA oversight. |
|  | Ensure adequate and proper core team usage. |
|  | Review conceptual study report to ensure the scope is consistent with the purpose and need. |
|  | Review conceptual study report to ensure the scope is consistent with MoDOT’s long-range transportation direction. A programming exception may be required. |
|  | Review and comment upon draft project scoping memorandum. |
|  | Ensure the correct design criteria from Fig. 4-04.1, Fig. 2-01.3, Fig. 2-01.5, or Fig 4-07.1 of the PDM has been used to the extent possible. |
|  | Ensure design exceptions have been approved for all criteria not meeting the appropriate standards of the PDM. |
|  | Review preliminary plans to ensure the scope is consistent with the purpose and need. |
|  | Review preliminary plans to ensure the scope is consistent with MoDOT’s long-range transportation direction. |
|  | Review and comment upon final project scoping memorandum. |

# Environmental

|  | Determine required environmental classification. (CE, EA, EIS) |
| --- | --- |
|  | Determine status of environmental document. (If the environmental document was approved more than three years previous, and the project remained inactive, there is a need to reevaluate the document for scope changes or changes in proposed mitigation. |
|  | Review and approve Cultural Resource/Section 106 documentation. |

# Bridge

|  | Review and comment on Type, Size and Location (TS&L) report. |
| --- | --- |
|  | Determine eligibility for the Highway Bridge Replacement and Rehabilitation Program. |
|  | Verify vertical clearance with Military Traffic Management Command (MTMC). |
|  | Consider necessary Coast Guard or Corps of Engineers permits. |

# Design/Roadway

|  | Evaluate Access Modifications to the Interstate system. (May require an Access Justification Report – see FHWA August 17, 2001 letter) |
| --- | --- |
|  | Consider the Pavement Type Selection or pavement rehabilitation strategy. |
|  | Check project for Proprietary/Public Interest Finding/Buy America items. |
|  | Ensure environmental commitments from Environmental Document are included in the project. |
|  | Check Railroad operations. |
|  | Check Traffic Control Plan. |
|  | Consider need for contract incentives or disincentives to minimize construction time. |
|  | Check Bicycle and Pedestrian accommodation. |
|  | Check for ADA compliance. |

# Traffic

|  | Determine if safety upgrades are included in the project. |
| --- | --- |
|  | Ensure accident/operational analysis has been performed. |
|  | Ensure the project is in compliance with the Manual on Uniform Traffic Control Devices (MUTCD). |
|  | Ensure access management guidelines are considered. |
|  | Consider any Intelligent Transportation Systems (ITS) elements included in the project. |
|  | Ensure the project is in conformity with the ITS National Architecture. |
|  | Ensure the project utilizes FHWA adopted ITS Standards. |
|  | Ensure the Conformity Documentation Checklist has been completed. |

# Right-of-way

|  | Advise MoDOT how Airspace Agreements, Functional Replacements, Hardship/Protective Purchase Acquisitions, Federal Land Transfers, and License Agreements may affect the scope of the project. |
| --- | --- |

For questions, comments, or suggested revisions to this checklist, please contact a Project Development Liaison Engineer