## MoDOT Consultant Invoice
MoDOT Consultant Services Invoice
INVOICE
Invoice Date: |  |  |  |  | 2012-07-06
Invoice Number: |  |  |  |  | 3
Billing Period: |  |  |  |  | 6/1/12-6/30/12
Project Number: |  |  |  |  | J5B0800C
Section 1: Project Information
Consultant Information
Consultant Firm Name: |  | ABC Engineering
Consultant Contact Name: |  | Jane Doe
Address 1: |  | PO Box 3333
Address 2: |  | 105 W 7th Street, Suite A
City, State, Zip: |  | Nowhere, USA 65555
Phone Number: |  | 573-555-5555
Contact Email: |  | johndoe@engineer.com
Consultant Project No.: |  | modot-sldist-555-998
Project Information
Project Description: |  | Route 100 widening & overlay
Project County: |  | Franklin
Engineering Services Contract Information
ESC Execution Date: |  | 2012-05-01
ESC Completion Date for PE Work Only: |  | 2012-11-07
ESC Completion Date for CE Work Only: |  | n/a
Original ESC Contract Amount: |  | 65000
Supplemental No._1_ Amount: |  | 7000
Supplemental No.__ Amount: |  | 0
Supplemental No.__ Amount: |  | 0
Maximum Amount for ESC: |  | 72000
Section 2: Billing Summary
Total Direct Salaries (see Section 3) |  |  | 2085
Overhead |  | 125% | 2606.25
|  |  | Subtotal 1 |  | 4691.25
Total Fixed Fee in Contract |  | 7500
Total fixed fee for this billing period |  |  | 700
Total fixed fee billed to date (including this period) |  | 975
|  |  | Subtotal 2 |  | 700
Total Direct Costs (see Section 3) |  |  | 5541.37
|  |  | Subtotal 3 |  | 5541.37
TOTAL to be paid for this invoice |  |  |  |  | 10932.62
Previously Total Invoiced Amount | 2750.87
Total Paid to Date (including this invoice) | 13683.49
MoDOT Consultant Services Invoice
INVOICE
Invoice Date: |  |  |  |  | 2012-07-06
Invoice Number: |  |  |  |  | 3
Billing Period: |  |  |  |  | 6/1/12-6/30/12
Federal Project Number: |  |  |  |  | J5B0800C
Section 3: Project Cost Breakdown
DIRECT SALARIES
Task Description/Employee/ Employee job Title | HOURS | RATE | AMOUNT
Prelim Plan/Jimmy John/Hwy Des I | 60 | 25.5 | 1530
Surveying/Stanley Smith/Surveyor II | 30 | 18.5 | 555
0
0
0
0
0
0
0
|  | Total Direct Salaries due this invoice | 2085
DIRECT COSTS-Sub-consultants & Other direct costs
Task Description/Sub-consultant firm name (**Denotes DBE Sub) |  |  | AMOUNT
Geotech Investigation/Soils-R-Us** |  |  | 5500
Other Direct Costs
Printing |  |  | 41.37
|  | Total Direct costs due this Invoice | 5541.37
MoDOT Consultant Services Invoice
INVOICE
Invoice Date: |  |  |  |  | 2012-07-06
Invoice Number: |  |  |  |  | 3
Billing Period: |  |  |  |  | 6/1/12-6/30/12
Federal Project Number: |  |  |  |  | J5B0800C
Section 4: Progress Report - % Complete & DBE
Total Costs (includes Salaries, Sub-consultants & Direct Costs)
Task | Total Budgeted | Total Expended to Date | Percent Expended (Budgeted/ Expended) | Estimate % Task Complete (Deliverables)
Prelim Plans | 7500 | 2500 | 33.33% | 50
Final Plans | 45000 | 0 | 0% | 0
Surveying | 2500 | 555 | 22.2% | 25
Geotech | 10000 | 5500 | 55% | 50
Supplemental #1 - ROW acquisition | 7000 | 0 | 0% | 0
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
TOTAL | 72000 | 8555 | 11.88%
DBE Verification – Summary To Date
DBE Goal | 10%
Prime Consultant Contract Total = | 72000
DBE Target $ Amount = | 7200
DBE Sub-Consultant | Subcontract Amount | Total $ Billed to Date | Overall DBE % Met to Date
Soils-R-Us | 10000 | 5500
Total DBE Contract $ | 10000
Total $ Billed to Date |  | 5500
DBE % Met to Date |  |  | 7.639%
Progress Report – Narrative
Surveying - have started surveying and will finish by 7/31/12. Prelim Plans have started and are 50% complete. A set of prelim plans will be sent to MoDOT on 8/1/12 for review. Geotech field investigations are underway with approx 50% completed. A report will be submitted to MoDOT by 10/1/12. We are tracking to exceed our DBE goal of 10%, to date we have met 7.64% of the 10% goal and expect to meet approx 13% by contract completion.