JOB SPECIAL PROVISIONS TABLE OF CONTENTS

(Job Special Provisions shall prevail over General Provisions whenever in conflict therewith.)

- General

- Contract Liquidated Damages

- Work Zone Traffic Management Plan

- Supplemental Revisions

- Project Contact for Contractor/Bidder Questions

F.	Bridge End Transitions

G. 	Safety Edge

H.	Quality Control for Plant Mix Bituminous Surface Leveling

I.	Quality Management

J.   Safety Plan

K.  Pavement Marking Log (if applicable)

L.	Additional Flaggers (if applicable)

M.  Winter Months Requirements (if applicable)

| “THIS MEDIA SHOULD NOT BE CONSIDERED A CERTIFIED DOCUMENT.” | MISSOURI HIGHWAYS AND TRANSPORTATION COMMISSION 105 W. CAPITOL AVE. JEFFERSON CITY, MO 65102 Phone 1-888-275-6636 |
| --- | --- |
|  | If a seal is present on this sheet, JSP’s have been electronically sealed and dated. |
|  | JOB NUMBER: COUNTY, MO DATE PREPARED: |
|  | ADDENDUM DATE: |
| Only the following items of the Job Special Provisions (Roadway) are authenticated by this seal: |  |

JOB

###### SPECIAL PROVISION

A.	GENERAL - FEDERAL JSP-09-02A

1.0  Description.  The Federal Government is participating in the cost of construction of this project.  All applicable Federal laws, and the regulations made pursuant to such laws, shall be observed by the contractor, and the work will be subject to the inspection of the appropriate Federal Agency in the same manner as provided in Sec 105.10 of the Missouri Standard Specifications for Highway Construction with all revisions applicable to this bid and contract.

1.1  This contract requires payment of the prevailing hourly rate of wages for each craft or type of work required to execute the contract as determined by the Missouri Department of Labor and Industrial Relations, and requires adherence to a schedule of minimum wages as determined by the United States Department of Labor.  For work performed anywhere on this project, the contractor and the contractor’s subcontractors shall pay the higher of these two applicable wage rates. State Wage Rates, Information on the Required Federal Aid Provisions, and the current Federal Wage Rates are available on the Missouri Department of Transportation web page at www.modot.org under "Bidding".  Effective Wage Rates will be posted 10 days prior to the applicable bid opening.  These supplemental bidding documents have important legal consequences.  It shall be conclusively presumed that they are in the bidder's possession, and they have been reviewed and used by the bidder in the preparation of any bid submitted on this project.

1.2  The following documents are available on the Missouri Department of Transportation web page at www.modot.org under "Business"; “Standards and Specifications”. The effective version shall be determined by the letting date of the project.

General Provisions & Supplemental Specifications

Supplemental Plans to October 2009 Missouri Std. Plans

For Highway Construction

These supplemental bidding documents contain all current revisions to the bound printed versions and have important legal consequences.  It shall be conclusively presumed that they are in the bidder's possession, and they have been reviewed and used by the bidder in the preparation of any bid submitted on this project.

B.	CONTRACT LIQUIDATED DAMAGES  JSP-13-01B

1.0  Description.  Liquidated Damages for failure or delay in completing the work on time for this contract shall be in accordance with Sec 108.8.  The liquidated damages include separate amounts for road user costs and contract administrative costs incurred by the Commission.

2.0  Period of Performance.  Prosecution of work is expected to begin on the date specified below in accordance with Sec 108.2.  Regardless of when the work is begun on this contract, all work shall be completed on or before the date specified below.  Completion by this date shall be in accordance with the requirements of Sec 108.7.1.

Notice to Proceed:	Month XX, 20XX

Completion Date:	Month XX, 20XX

2.1  Calendar Days.  The count of calendar days will begin on the date the contractor starts any construction operations on the project.

Job Number	Calendar Days	Daily Road User Cost

JXXXXX	XX	$XXX

JXXXXX	XX	$XXX

JXXXXX	XX	$XXX

JXXXXX	XX	$XXX

*** (If Calendar Days do not apply to the Job No., enter N/A for the number of Calendar Days) ***

3.0  Liquidated Damages for Contract Administrative Costs.  Should the contractor fail to complete the work on or before the completion date specified in Section 2.0, or within the number of calendar days specified in Section 2.1, whichever occurs first, the contractor will be charged contract administrative liquidated damages in accordance with Sec 108.8 in the amount of $XX per calendar day for each calendar day, or partial day thereof, that the work is not fully completed.  For projects in combination, these damages will be charged in full for failure to complete one or more projects within the above specified completion date or calendar days.

4.0  Liquidated Damages for Road User Costs.  Should the contractor fail to complete the work on or before the completion date specified in Section 2.0, or within the number of calendar days specified in Section 2.1, whichever occurs first, the contractor will be charged road user costs in accordance with Sec 108.8 in the amount specified in Section 2.1 for each calendar day, or partial day thereof, that the work is not fully completed.  These damages are in addition to the contract administrative damages and any other damages as specified elsewhere in this contract.

C.	WORK ZONE TRAFFIC MANAGEMENT PLAN

1.0  Description.  Work zone traffic management shall be in accordance with applicable portions of Division 100 and Division 600 of the Standard Specifications, and specifically as follows.

2.0  Traffic Management Schedule.

2.1  Traffic management schedules shall be submitted to the engineer for review prior to the start of work and prior to any revisions to the traffic management schedule.  The traffic management schedule shall include the proposed traffic control measures, hours traffic control will be in place, and work hours.

2.2  The contractor shall notify the engineer prior to lane closures or shifting traffic onto detours.

2.3  The engineer shall be notified as soon as practical of any postponement due to weather, material or other circumstances.

2.4  In order to ensure minimal traffic interference, the contractor shall schedule lane closures for the absolute minimum amount of time required to complete the work.  Lanes shall not be closed until material is available for continuous construction and the contractor is prepared to diligently pursue the work until the closed lane is opened to traffic.

2.5	Traffic Delay.   The contractor shall be responsible for maintaining the existing traffic flow through the job site during construction.  If disruption of the traffic flow occurs and traffic is backed up in queues of 15 minute delays or longer, then the contractor shall review the construction operations which contributed directly to disruption of the traffic flow and make adjustments to the operations to prevent the queues from occurring again.

3.0  Work Hour Restrictions.

3.1  There are three major summer holiday periods:  Memorial Day, Independence Day, and Labor Day.  All lanes shall be scheduled to be open to traffic during these holiday periods, from 12:00 noon on the last working day preceding the holiday until 9:00 a.m. on the first working day subsequent to the holiday.

3.2  The contractor shall not perform any construction operation on the active lanes during restricted periods, holiday periods or other special events specified in the contract documents.

3.2  The contractor shall not perform any work between the hours of ½ hour before sunset until ½ hour after sunrise. No night time work will be allowed without submission of an adequate traffic control plan to cover nighttime operations and prior approval by the engineer

4.0  Basis of Payment.  No direct payment will be made to the contractor to recover the cost of equipment, labor, materials or time required to fulfill the above provisions, unless specified elsewhere in the contract document.

D.	SUPPLEMENTAL REVISIONS

(To be inserted by Central Office)

E.	PROJECT CONTACT FOR CONTRACTOR/BIDDER QUESTIONS   JSP-96-05

All questions concerning this project during the bidding process shall be forwarded to the project contact listed below.

________________________, Project Contact

________________________ District

__________________

_________________

Telephone Number __-__-__

e-mail  xxxxx@modot.mo.gov

All questions concerning the bid document preparation can be directed to the Central Office  – Design at (573) 751-2876.

F.	BRIDGE END TRANSITIONS

1.0  At all bridge exceptions, the engineer will determine in the field the ending point of the transition. This point will not necessarily be at the bridge end, but will be located at a point which provides the smoothest transition and approach to the bridge.  Where bridges are to be resurfaced, the surfacing shall be from curb to curb.

G	SAFETY EDGE  JSP-12-08

1.0 Description.  An approved longitudinal shoulder wedge system shall be used to create a beveled edge between the paved lane and the shoulder.

2.0 Construction Requirements.  The shoulder wedge system shall result in a bevel measuring 30 degrees from horizontal and extending laterally from the nominal edge of traveled way to the point of intersection with the inslope.  The construction tolerance shall be plus or minus 5 degrees.

2.1  The shoulder wedge system shall maintain contact between the device and road shoulder surface and allow automatic transition to cross roads, driveways and obstructions.  The device must be removable or be able to be lifted when not in use.

2.2  All shoulder wedge systems to be used for the purpose of creating a Safety Edge must be approved by the engineer.  The device must be designed to constrain the asphalt material and increase the consolidation of the extruded profile.  The use of a conventional single plate strike-off is not permitted.

3.0 Basis of Payment.  The accepted quantities of pavement will be paid for at the contract unit price.  There will be no direct payment for compliance with the requirements of this provision.

H 	QUALITY CONTROL FOR PLANT MIX BITUMINOUS SURFACE LEVELING (Version 08/2013)

1.0  Description.  The contractor shall provide Quality Control for the production and placement of Plant Mix Bituminous Surface Leveling Mixture in accordance with the Quality Management Job Special Provision, Section 402, and as stated herein.

2.0  Asphalt Plant Requirements.  The contractor shall perform all quality control inspection and testing in the production of the Surface Leveling Mixture.  All reports shall include the Contract ID, Project Number, Route, County, and Job Mix number.

2.1  Calibration of the asphalt plant shall be in accordance with Section 403.17.2.2.  Record retention for verification of test reports shall be in accordance with 403.17.3.2.

2.2  At a minimum, QC shall perform one sieve analysis test for each day of production of Surface Level mixture in excess of 100 tons to verify the aggregate is within the required gradation range.  Results of the QC sieve analysis test shall be reported to the engineer daily.  A split of each sample shall be clearly labeled and stored by QC in a manner that prevents contamination.  QA will collect a minimum of one random QC split sample, and one full sample from plant production, for testing per each 10,000 tons of production.  Uncollected QC split samples shall be retained by QC until the engineer authorizes disposal or until the Final Inspection, whichever occurs earlier.

2.3  QC shall monitor the quantity of asphalt binder used in the production of the mix, including any commercial mix, and report that quantity to the engineer.  Original asphalt binder delivery tickets shall accompany the report submitted to the engineer.  QA will perform a minimum of one asphalt binder content test per each 10,000 tons of production for any project that exceeds a total of 5,000 tons of production.

2.4  QC shall take a daily sample of the asphalt binder per instructions in Section 460.3.13 of the EPG. The engineer will collect the QC samples and ship to the MoDOT Central lab for random testing.  In addition, QA will take a minimum of one random sample per project from the binder line. The QA sample will be shipped to the Central Lab along with the daily samples and will be designated for testing.

2.5  QC shall perform one moisture content test for each day of production of Surface Level mixture in excess of 100 tons.  The frequency of the moisture test may be reduced at the discretion of the Quality Manager if approved by the engineer.

3.0  Roadway Requirements.  The contractor shall perform all quality control inspection of the Surface Leveling Mixture on the roadway and shall monitor the asphalt tonnage placed in relation to plan quantity.

3.1  Irregularities.  Additional tons of Surface Leveling mix will be provided for irregularities in the existing roadway surface.  The tonnage specified for irregularities is an estimated quantity and shall only be placed at locations where it is necessary to fill ruts and other low points.  Prior to placing the mix, the contractor and QA shall evaluate the entire route and develop a plan that best utilizes the tonnage needed for irregularities.  Any excess quantity of irregularities shall not be placed.

3.2  Tack.  On the first day of production, the contractor shall demonstrate proper application of tack coat in the presence of QC and QA.  Thereafter, when QA is not present to witness the application of the tack coat, QC shall document the tack application by taking a minimum of two high-resolution date/time stamped photographs of the tacked surface per one-mile segment.  Pictures should be taken just in front of the paver in order to account for loss of tack from truck tires.  QC shall also monitor and document the application rate.  QC shall take distributor readings at the beginning and ending of each shift and document the quantity used.

3.3  Spreading and Rolling.  On the first day of production, the contractor shall demonstrate successful spreading and compaction of the mixture, including proper rolling patterns, in the presence of QC and QA.  Thereafter, QC shall monitor all roadway production procedures and document daily.

3.4  Monitoring of Quantity.  QC shall monitor the quantity of Surface Level mix placed and report that information to the engineer and production staff as specified herein.

3.4.1  QC shall verify that the quantity of Surface Leveling mix in the contract for each route is sufficient to cover the roadway as shown on the typical sections, including any surface irregularities.  Any discrepancies shall be brought to the engineer's attention in writing prior to the pre-construction conference.  Plan quantity shall be defined as the total tons computed to cover the surface area according to the typical section, plus any amount pre-approved by the engineer for pavement irregularities.

3.4.2  QC shall provide temporary log mile reference points at no less than ½ mile intervals along each route to monitor the tons of Surface Leveling mix laid in relation to plan quantity.    Entrances, shoulders, or other irregular areas will be monitored as directed by the engineer.

3.4.3  During production, QC shall document the total tons placed in each one-mile segment, along with the plan quantity and the percent over/under for that segment. The cumulative quantity and percent over/under for the route should also be documented.  After each one-mile segment, QC shall provide a status report to the contractor's production manager and the engineer.  When the engineer is not present on the project, QC shall send an electronic status report to the engineer.

3.4.4  The goal is to keep the placed quantity within 2% of plan quantity for the project.  The engineer will monitor the status reports from QC and will advise the contractor on how to proceed when there is an excessive variance from plan quantity.  The engineer may decrease the frequency of the electronic status reports when the variances are consistently low.

3.4.5  QC shall collect asphalt tickets from the delivery trucks and group them per each one-mile segment.  QC shall submit to the engineer a daily summary report that includes all of the information specified in Sec 3.4.3.  The QC inspector shall sign the summary report confirming that the information is accurate and that the attached tickets represent the asphalt material placed.

3.4.6  The contractor shall be responsible for providing and maintaining a reliable means of immediate communication with the engineer.  The engineer will be equipped with a commission-furnished cellular phone or a land line when not present on the project.

4.0  Excessive Quantity.  If the contractor places Surface Level mix on any one-mile segment, or any other isolated areas, in excess of plan quantity by 5% or more, without prior approval from the engineer, further investigation may be required to determine if the excess was warranted.  If directed by the engineer, the contractor shall core the pavement at locations established by the engineer to determine the amount that was excessive, if any.  No payment will be made for the cost to core the pavement or for the tons of Surface Level mix that the engineer determines to be excessive. If the mix is determined to be justified, payment will be made for the mix, and for the cost of coring at the fixed price established in Sec 109.  Placement of asphalt in excess of plan quantity for two consecutive segments without prior approval from the engineer may result in issuance of an Order Record to stop work.

5.0  Basis of Payment.  No direct payment will be made for compliance with this provision.  All costs shall be considered completely covered under the pay items provided in the contract.

I	QUALITY MANAGEMENT  NJSP-15-22 (07/2014)

1.0  Quality Management.  The contractor shall provide Quality Management as specified herein to ensure the project work and materials meets or exceeds all contract requirements.

1.1  The contractor shall provide Quality Control (QC) of the work and material, as specified herein, to ensure all work and material is in compliance with contract requirements.  QC staff shall perform and document all inspection and testing.  The QC inspectors and testers may be employed by the contractor, sub-contractor, or a qualified professional service provided by the contractor.

1.2  The engineer will provide Quality Assurance (QA) inspection.  The role of QA is to verify the performance of QC and provide confidence that the product will satisfy given requirements for quality.

1.3  The contractor shall designate a person to serve as the project Quality Manager (QM).  The QM shall be knowledgeable of standard testing and inspection procedures for highway and bridge construction, including a thorough understanding of the Missouri Standard Specifications.  The QM shall be responsible for the implementation and execution of the Quality Management Plan and shall oversee all QC responsibilities, including all sub-contract work.  The QM shall be the primary point of contact for all quality related issues and responsibilities, and shall ensure qualified QC technicians and inspectors are assigned to all work activities.  The QM should be separate from the manager of the work activities to effectively manage a QC program.

1.4  Any QC personnel determined in sole discretion of the engineer to be incompetent, derelict in their duties, or dishonest, shall at a minimum be removed from the project.  Further investigation will follow with a stop work notification to be issued until the contractor submits a corrective action report that meets the approval of the engineer.

2.0  Quality Management Plan.  The contractor shall develop, implement and maintain a Quality Management Plan (QMP) that will ensure the project quality meets or exceeds all contract requirements, and provides a record for acceptance of the work and material.  A sample QMP, which shows minimum requirements, is provided on the MoDOT website at:  http://www.modot.org/quality.

2.1  The QMP shall address all QC inspection and testing requirements of the work as described herein.  A draft QMP shall be submitted to the Resident Engineer for review at least two weeks prior to the pre-construction conference.  An approved QMP is required at least two weeks prior to the start of work, unless otherwise allowed by the engineer.  Physical work on the project shall not begin prior to approval of the QMP by the engineer.

2.2  The approved QMP shall be considered a contract document and any revisions to the QMP will require approval from the engineer.

  - The following items shall be included in the Quality Management Plan:

- Organizational structure of the contractor’s project management, production staff, and QC staff, specific to this project.

- Name, qualifications and job duties of the Quality Manager.

- A list of all certified QC testers who will perform QC duties on the project, including sub-contract work, and the tests in which they are certified.

- A list of all QC inspectors who will perform QC inspection duties on the project, including sub-contract work, and the areas of inspection that they will be assigned.

- A procedure for verifying documentation is accurate and complete as outlined in Section 3.

- A procedure describing QC Inspections as outlined in Section 4.

- A procedure describing QC Testing, as outlined in Section 5, including a job specific Inspection and Test Plan (ITP).

- A procedure describing Material Receiving as outlined in Section 6.

- A list of Hold Points that are not included in the checklist forms, as outlined in Section 8.

- A procedure for documenting and resolving Non-Conforming work as outlined in Section 9.

- A procedure for tracking and documenting revisions to the QMP.

- A list of any approved changes to the Standard Specifications or ITP, including a reference to the corresponding change order.

- Format for the Weekly Schedule and Work Plans as outlined in Section 10, including a list of activities that will require pre-activity meetings.

3.0  Project Documentation.  The contractor shall establish a Document Control Procedure for producing and uploading the required Quality Management documents to a MoDOT-provided server.  The document management software used by MoDOT is Microsoft SharePoint®.  Contractors do not need to purchase Microsoft SharePoint®, however, it is recommended that new users acquire some basic training to better understand how to use this software.  MoDOT does not provide the software training, but there are several online vendors who do.  Contractors are required to use Microsoft Excel® and Microsoft Word® with some documents.

3.1  The contractor shall utilize the file structure and file naming convention provided by MoDOT.  A sample file structure is available on the MoDOT website.

3.2  Documents (standard forms, reports, and checklists) referenced throughout this provision are considered the minimum documentation required.  They shall be obtained from MoDOT at the following web address:  http://www.modot.org/quality . The documents provided by MoDOT are required to be used in the original format, unless otherwise approved by the engineer.  Any alteration to these forms shall be approved by the engineer.

3.3  Timely submittal of the required documents to the MoDOT document storage location is essential to ensure payment can be processed for the completed work.  Submittal of the documents is required within 12 hours of the work shift that the work was performed, or on a document-specific schedule approved by the engineer and included in the QMP.

3.4  The contractor shall establish a verification procedure that ensures all required documents are submitted to the engineer within the specified time, and prior to the end of each pay period for the work that was completed during that period.  Payment will not be made for work that does not include all required documents.  Minimum documents that might be required prior to payment include: Test Reports, Inspection Checklists, Materials Receiving Reports, and Daily Inspection Reports.

3.5  The contractor shall perform an audit at project closeout to ensure the final collection of documents is accurate and complete.

4.0  Quality Control Inspections. The QMP shall identify a procedure for performing QC inspections.  QC inspections shall be performed for all project activities to ensure the work is in compliance with the contract, plans and specifications.

4.1  The QM shall identify the QC inspectors assigned to each work activity.  The QC inspectors shall inspect the work to ensure the work is completed in accordance with the plans and specifications, and shall document the inspection by completing the required inspection checklists, forms, and reports provided by MoDOT.  Depending on the type of work, the checklists may be necessary daily, or they may follow a progressive work process.  The frequency of each checklist shall be stated in the QMP. The contractor may propose alternate versions of checklists that are more specific to the work.

4.2  A Daily Inspection Report (DIR) is required to document pertinent activity on the project each day.  This report shall include a detailed diary that describes the work performed as well as observations made by the inspection staff regarding quality control.  The report shall include other items such as weather conditions, location of work, installed quantities, tests performed, and a list of all subcontractors that performed work on that date.  The report shall include the full name of the responsible person who filled out the report and shall be digitally signed by an authorized contractor representative.

4.3  External fabrication of materials does not require further QC inspection if the product is currently under MoDOT inspection or an approved QC/QA program.  QC inspection and testing required in the production of concrete for the project shall be the responsibility of the contractor.

4.4  The contractor shall measure, and document on the DIR, the quantity for all items of work that require measurement.  Any calculations necessary to support the measurement shall be included with the documentation.  The engineer will verify the measurements prior to final payment.

5.0  Quality Control Testing.  The QMP shall identify a procedure for QC testing.  The contractor shall perform testing of the work at the frequency specified in the Inspection and Test Plan (ITP).

5.1  MoDOT will provide a standard ITP and the contractor shall modify it to include only the items of work in the contract, including adding any Job Special Provision items.  The standard ITP is available on the MoDOT website at http://www.modot.org/quality.  The contractor shall not change the specifications, testing procedures, or the testing frequencies, from the standard ITP without approval by the engineer and issuance of a change order.

5.2  Test results shall be recorded on the standard test reports provided by the engineer, or in a format approved by the engineer.  Any test data shall be immediately provided to the engineer upon request at any time, including prior to the submission of the test report.

5.3  The contractor shall ensure that all personnel who perform sampling and/or testing are certified by the MoDOT Technician Certification Program or a certification program that has been approved by MoDOT for the sampling and testing they perform.

5.4  If necessary, an independent third party will be used to resolve any significant discrepancies between QC and QA test results.  All dispute resolution testing shall be performed by a laboratory that is accredited in the AASHTO Accreditation Program in the area of the test performed.  The contractor shall be responsible for the cost to employ the third party laboratory if the third party test verifies that the QA test was accurate.  The Commission shall be responsible for the cost if the third party test verifies that the QC test was accurate.

6.0   Material Receiving.  The QMP shall identify a procedure for performing material receiving.  Standard material receiving forms will be provided by the engineer.

6.1  The procedure shall address inspections for all material delivered to the site (excluding testable material such as concrete, asphalt, aggregate, etc.) for general condition of the material at the time it is delivered.  The material receiving procedure shall record markings and accompanying documentation indicating the material is MoDOT accepted material (MoDOT-OK Stamp, PAL tags, material certifications, etc.).

6.2  All required material documentation must be present at the time of delivery.  If the material is not MoDOT accepted, the contractor shall notify the engineer immediately and shall not incorporate the material into the work.

7.0  Quality Assurance.  The engineer will perform Quality Assurance inspection and testing (QA) to verify the performance of QC inspection and testing.  The frequency of the QA testing will be as shown in the ITP, but may be more frequent at the discretion of the engineer.  The engineer will record the results of the QA testing and inspection and will inform the contractor of any known discrepancies.

7.1  QA is responsible for verifying the accuracy of the final quantity of all pay items in the contract.  This includes taking measurements on items that require measurement and other items that are found to have appreciable errors.

7.2  QA inspection and test results shall not be used as a substitute for QC inspection and testing.

7.3  QA will be available for Hold Point inspections at the times planned in the Weekly Schedule.  The inspections may be re-scheduled as needed, but a minimum 24-hour advance notification from the contractor is required unless otherwise approved by the engineer.

8.0  Hold Points.  Hold Points are events that require approval by the engineer prior to continuation of work.  Hold Points occur at definable stages of work when the succeeding work depends on a QA review of the preceding work before work can continue.

8.1  A list of minimum Hold Points will be provided by the engineer and shall be included in the QMP.  The engineer may make changes to the Hold Point list at any time.

8.2  Prior to all Hold Point inspections, QC shall provide the engineer with the Daily Inspection Reports, Inspection Checklists, Test Reports, and Material Receiving Reports for the work performed leading up to the Hold Point.  If the engineer identifies any corrective actions needed during a Hold Point inspection, the corrections shall be completed prior to continuing work.  The engineer may require a new Hold Point to be scheduled if the corrections require a follow-up inspection.

9.0  Non-Conformance Reporting.  Non-conformance reports shall be issued by the contractor for work that does not meet the contract requirements.  Non-conforming work includes work, testing, materials and processes that do not meet contract requirements.  The contractor shall establish a procedure for identifying and resolving non-conforming work as well as tracking the status of the reports.

9.1  Contractor QC staff or production staff should identify non-conforming work and document the details on the Non-Conformance Report form provided by MoDOT.  QA staff may also initiate a non-conformance report.

9.2  In-progress work that does not meet the contract requirements may not require a non-conformance report if production staff is aware of the issue and corrects the problem during production.  QC or QA may issue a non-conformance report for in-progress work when documentation of the deficiency is considered beneficial to the project record.

9.3  The contractor shall propose a resolution to the non-conforming work.  Acceptance of a resolution by the engineer is required before closure of the non-conformance report.

9.4  For recurring non-conformance work of the same or similar nature, a written Corrective Action Request will be issued by QC or QA.  The contractor shall then establish a procedure for tracking the corrective action from issuance of the request to implementation of the solution.  Approval from the engineer is required prior to implementation of the proposed corrective action.  The contractor shall notify the engineer after the approved corrective action has been implemented.

10.0  Work Planning and Scheduling.  The contractor shall include Quality Management in all aspects of the work planning and scheduling.  This shall include providing a Weekly Schedule, a Work Plan for each work activity, and holding pre-activity meetings for each new activity.

10.1  A Weekly Schedule shall be provided to the engineer each week that outlines the planned project activities for the following two-week period.  This schedule shall include all planned work, identification of all new activities, traffic control events, and requested Hold Point inspections for the period.  Planned quantity of materials, along with delivery dates should also be included in the schedule.

10.2  A Work Plan shall be submitted to the engineer at least one week prior to the pre-activity meeting.  The Work Plan shall include the following: a safety plan, list of materials to be used, work sequence, defined responsibilities for QC testing and inspection personnel, and stages of work that will require Hold Point inspections.

10.3   A pre-activity meeting is required prior to the start of each new activity. The purpose of this meeting is to discuss details of the Work Plan and schedule, including all safety precautions.  Those present at the meeting shall include:  the production supervisor for the activity, the Quality Manager, QC inspection and testing staff, and QA.  The Quality Manager will review the defined responsibilities for QC testing and inspection personnel and will address any quality issues with the production staff.  Attendees may join the meeting in person or by phone or video conference.

11.0  Basis of Payment.  Payment for all costs associated with developing, implementing and maintaining the Quality Management Plan, providing Quality Control inspection and testing, and all other costs associated with this provision, will be considered included in the unit price of each contract item.  No direct pay will be made for this provision.

J	SAFETY PLAN

1.0  Description.  This contractor shall submit to the engineer a project Safety Plan (SP) for all work performed by the contractor and all subcontractors.  The purpose of the SP is to encourage and enable all work to be performed in the safest possible manner and that all parties involved are aware of their individual responsibility for safety on the jobsite.

1.1  The SP shall be completed by the contractor and provided to the engineer prior to the beginning of any construction activity or phase on the project.

1.2  The contractor shall designate a person to serve as Project Safety Manager (PSM). The PSM shall be responsible for implementing and overseeing the SP. The PSM is not required to be present on the project at all times, but must be available to address safety issues and needs.

1.3  The PSM shall make revisions to the SP as necessary.  Any new project activities or phases shall be included in the SP prior to work beginning on that activity or phase.

1.4  An example Safety Plan is available at: www.modot.org/safetyplan

2.0 Emergency Preparedness.  The SP shall outline and detail for all workers, the specific procedures and actions necessary to respond to a jobsite emergency and the measures taken to communicate these requirements to all workers.

2.1  The SP shall include a list of local emergency contacts including phone numbers.  A copy of the emergency contact list shall be accessible to workers.

2.2  In the case where there is no cellular or land line phone service at the jobsite, the SP shall identify how to reach the nearest available phone service.

3.0  Project Safety Analysis.  The SP should contain a basic Project Safety Analysis (PSA) that outlines the actions necessary to complete each activity or phase of the project.  The SP shall include a general description of the primary activities or steps required to safely complete the project.

3.1  Each activity should also include a general description of the work involved along with the known risks associated with the activity.  In addition the PSA should outline the controls for those risks, including any Personal Protection Equipment (PPE) requirements for that activity or phase, and whether or not the activity or phase requires a specific safety meeting prior to beginning the activity or phase.

3.2  Submittal of the PSA for all activities or phases is not required with the initial submittal of the SP; however, the PSA for each activity or phase shall be completed prior to the beginning of that activity or phase.

4.0  Safety Meetings. The SP shall include the types of safety meetings that will be required of and conducted by the contractor.

5.0  Safety Training.   The SP shall identify the required safety training provided to the contractor’s personnel. The contractor shall require that the appropriate safety training for the contractor’s personnel is completed prior to the beginning of work on each activity or phase.

5.1   The SP shall identify the recommended safety training needs and PPE for MoDOT employees who will be exposed to the work activities. MoDOT will provide safety training and PPE to MoDOT employees based on MoDOT safety policies.

6.0  Payment.  There will be no direct payment for compliance with this Safety Plan provision.

K	PAVEMENT MARKING LOG(if applicable)

1.0  Description.  The contractor shall log the locations of existing pavement marking prior to any construction operations that may affect the existing pavement marking. The log shall contain all existing pavement marking and shall include center stripes, no passing stripes, lane lines, turn arrows, hash bars, cross walks, and stop bars. The contractor shall provide a copy of the existing pavement marking log to the engineer. The contractor shall place the new pavement marking at the same locations as the existing pavement marking, unless otherwise directed by the engineer or shown on the plans.

2.0  Basis of Payment.  No direct payment will be made for logging of existing pavement marking

L	ADDITIONAL FLAGGERS (if applicable)

1.0  Additional flagger(s) and appropriate construction signs shall be provided at each of the specified locations when work zone extends through the following intersections and/or approaches:

- XXXXX

- XXXXX

- XXXXX

2.0  Basis of Payment.  There will be no direct pay for all labor and equipment necessary to provide additional flaggers.  All cost shall be considered completely covered under the pay items provided in the contract.

Winter Months REQUIRMENTS JSP-15-07 (if applicable)

- Description.  This project contains work which spans the winter months.

- Work to be Completed.  When the contractor ceases operations for the winter months, any paving operation performed by the contractor shall not result in a lane height differential between adjacent lanes.

- Maintenance of Pavement Marking.  Prior to ceasing operations for winter months, a permanent or temporary stripe shall be provided on any completed length to the point that the original stripe was obliterated or obscured by the contractors operation.  Temporary striped areas shall be re-striped with the remaining route upon performance of the final striping.

- Winter Related Maintenance Activities.  The contractor shall have the project in a condition as not to interfere with the plowing of snow. The contractor shall also provide a taper at the end of his paving that will not be damaged by the plowing of snow.

- Basis of Payment.  There will be no direct pay for compliance with this provision.