## Sheet1
Transferring a MHTC Road and/or Bridge contract to another contractor. (Assignment Agreement - i.e., reassigning a contract to a different prime)
Initiating Action | Transfer Condition | CCO Agreement Type/No. | Name Change "Rider" for Bond Required | Bond | Power of Attorney | Insurance | Remarks
MoDOT will receive a notification from a contractor (Assignor) who has sold their company to another contractor (assignee) that is requesting the transfer (assignment) to be able to finish the contract, or a situation where a contractor (assignor) request the transfer to another contractor (assignee) because they have more work than possible to complete. (No Work has started in this scenario) | Receiving Contractor (Assignee) using Existing Surety of the original prime (Assignor) | CM14 (Requires Assignor, Assignee, Surety & MHTC to execute.) | Name change bond "Rider" required which will accompany Original bond. Rider content must be acceptable to MoDOT. The bond "rider" should be dated on or before the date the assignee executes the assignment agreement. | Original Bond does not Change. The existing surety issues a name change "rider" which replaces the name on the bond to the receiving contractor (assignee). | Use existing | New Certificate from receiving contractor (assignee) before commencing work. | Assignment agreement uploaded from eAgreements CCO sharepoint site and moved into Docusign. Order of signatures will be assigned by the Commission Secretarty's Office. The "rider" will need to be uploaded into docusign upon full execution of the assignment agreement. The Resident Engineer is notified of the prime contractor change on the contract and AASHTO Ware Project is updated to now show the new prime (assignee).
MoDOT will receive a notification from a contractor (Assignor) who has sold their company to another contractor (assignee) that is requesting the transfer (assignment) to be able to finish the contract. (This scenario assumes some work has started.) | Receiving Contractor (Assignee) using Existing Surety. In this situation the existing surety is agreeing to cover work of both the original contractor and the new contractor. This scenario recognizes that the original contractor has completed some of the contract, but the new contractor (assignee) intends to utilize the existing surety. This condition probably will only work if a minor amount of work is completed. This can work, but many times, the existing surety doesn't want to "one-time" bond a contractor that hasn't previously done business together. (If the existing surety disapproves, CM02 B-Modified should be used depending on the conditions.) | CM14 (Requires Assignor, Assignee, Surety & MHTC to execute.) | Name change bond "Rider" required to accompany Original bond. Rider content must be acceptable to MoDOT. The bond "rider" should be dated on or before the date the assignee executes the assignment agreement. | Original Bond does not Change. The existing surety issues a name change "rider" which replaces the name on the bond to the receiving contractor (assignee). | Use existing | New Certificate from receiving contractor (assignee) before commencing work. | Assignment agreement uploaded from eAgreements CCO sharepoint site and moved into Docusign. Order of signatures will be assigned by the Commission Secretarty's Office. The "rider" will need to be uploaded into docusign upon full execution of the assignment agreement. The Resident Engineer is notified of the prime contractor change on the contract and AASHTO Ware Project is updated to now show the new prime (assignee).
MoDOT will receive a notification from a contractor (Assignor) who has sold their company to another contractor (assignee) that is requesting the transfer (assignment) to be able to finish the contract, or a situation where a contractor (assignor) request the transfer to another contractor (assignee) because they have more work than possible to complete. (No Work has started in this scenario.) | Receiving Contractor (assignee) request to use a new surety to perform the contract work. | CM02 (Requires Assignor, Assignee & MHTC execution) | NA | Receiving contractor (assignee) will provide a new bond from their surety, in the original format of the existing bond. For this situation, the date and amount of the new bond must match exactly the original bond. | A new POA is required and must be dated with the same date of the original bond or before, otherwise, the POA has no authority. | New Certificate from receiving contractor (assignee) before commencing work. | Assignment agreement uploaded from eAgreements CCO sharepoint site and moved into Docusign. Order of signatures will be assigned by the Commission Secretary's Office. Upon full execution of the assignment agreement by MHTC, the original contractor (assignor) can request release of their bond, because the new surety for the new contractor (assignee) has provided a new bond in the full amount that matched the existing bond.
MoDOT will receive a notification from a contractor (Assignor) who has sold their company to another contractor (assignee) that is requesting the transfer (assignment) to be able to finish the contract. (In this scenario, a portion of the work is already completed by original contractor and all the remaining contract work will be perform by the assignee) | Receiving Contractor (assignee) request to use new surety . Typically, if this is a small amount of work, the new surety won't object to covering the amount of work already completed by the original contractor. (If the surety disapproves, CM02 B-modified should be used.) | CM02 (Requires Assignor, Assignee & MHTC execution) | NA | Receiving contractor (assignee) will provide a new bond from their surety, in the original format of the existing bond. For this situation, the date and amount of the new bond must match exactly the original bond. | A new POA is required and must be dated with the same date of the original bond or before, otherwise, the POA has no authority. | New Certificate from receiving contractor (assignee) before continuing work. | Assignment agreement uploaded from eAgreements CCO sharepoint site and moved into Docusign. Order of signatures will be assigned by the Commission Secretary's Office. Upon full execution of the assignment agreement by MHTC, the original contractor (assignor) can request release of their bond, because the new surety for the new contractor (assignee) has provided a new bond in the full amount that matched the existing bond.
MoDOT will receive notification from a contractor (assignor) who has sold to another contractor (assignee). If the new surety objects to covering the assignors completed work, then two bonds will likely need to remain in place. Contractors and sureties have long-standing relationships and if too much work has been completed, a new surety for the assigneee is not willing to take on the risk of the work completed by another contractor (in this case, the assignor). | Receiving Contractor (assignee) using a new surety for work yet to complete and the original bond remains in place for completed worked by the original contractor (assignor), up to the assignment execution date. | CM02 B-Modified (Requires Assignor, Assignee, Original and Completing Sureties & MHTC) | NA | Original bond remains in effect. The new bond will be dated as of the date the assignee executes the assignment or before. The value of the new bond must be calculated/estimated based on the amount of contract work remaining. The original bond provides coverage up to the assignment execution date, and not beyond, because it follows the contract. | Original POA remains in-place for the original bond. The new POA must be dated on or before the date of the new bond, both of which will be on or before the date of the assignment execution by the assignee. | New Certificate from receiving contractor (assignee) before continuing work. | Assignment agreement uploaded from eAgreements CCO sharepoint site and moved into Docusign. Order of signatures will be assigned by the Commission Secretary's Office. Two Bonds remain in-place through the completion of the contract and no bonds can be released.
Note on I14: Jay Bestgen: Scott, IN this scenario, the original bond has the total value, but the agreement notes there is a separation between old and new. Is this just not our problem.??