| Section 1: Project Information |  |  |  |  |
| --- | --- | --- | --- | --- |
| LPA Information |  |  |  |  |
| LPA Person of Responsible Charge: |  |  | John Doe |  |
| LPA Contact Phone: |  |  | (573) 999-9999 |  |
| LPA Contact Email: |  |  | lpa@lpa.com |  |
| Consultant Information |  |  |  |  |
| Consultant Contact Name: |  |  | Jane Doe |  |
| Address 1: |  |  | 123 Main St. |  |
| Address 2: |  |  | Box 111 |  |
| City, State, Zip: |  |  | Jefferson City, MO 65109 |  |
| Phone Number: |  |  | (573) 999-9999 |  |
| Contact Email: |  |  | xyzeng@xyz.com |  |
| Consultant Project No.: |  |  | 12345-5521 |  |
| Project Information |  |  |  |  |
| Project Description: |  |  | Sidewalk Project from Main Street to the intersection of Route 21 includes adjoining bridge |  |
| Project County: |  |  | Cole |  |
| Federal Project Number: |  |  | STP-9999 (999) |  |
| LPA Project Number: |  |  | 126-9963-2001 |  |
| PE Federal Obligation Date: |  |  | June 1, 2012 |  |
| Federal Funding Category(s): |  |  | STP/BRO/TE |  |
| Engineering Services Contract Information |  |  |  |  |
| ESC Execution Date: |  | May 6, 2012 |  |  |
| ESC Completion Date for PE Work Only: |  | March 1, 2013 |  |  |
| ESC Completion Date for CE Work Only: |  | March 1, 2014 |  |  |
| Original ESC Contract Amount: |  | $110,000.00 |  |  |
| Supplemental No.__ Amount: |  | $10,900.00 |  |  |
| Supplemental No.__ Amount: |  | n/a |  |  |
| Supplemental No.__ Amount: |  | n/a |  |  |
| Maximum Amount for ESC: |  | $120,900.00 |  |  |
|  | Section 2: Billing Summary Total Direct Salaries (see Section 3); $9,914.03. Overhead; 153.22%; $15,190.28. Subtotal 1; $25,104.31. Total Fixed Fee in Contract; $12,100.00. Total Fixed Fee PREVIOUSLY billed; $2,150.00. Total Fixed Fee for this period; $1,210.00. Subtotal 2; $1,210.00. Total Direct Costs (see Section 3); $12,573.84. Subtotal 3; $12,573.84. Total for this invoice; $38,888.15. Less non-participating costs; $0.00. TOTAL to be paid for this invoice; $38,888.15. Previously Total Invoiced Amount; $13,000.00. Total Paid to Date; $51,888.15. |

Section 3: Project Cost Breakdown

DIRECT SALARIES

| Task Description/Employee/Employee job Title or Category | HOURS | RATE | AMOUNT |
| --- | --- | --- | --- |
| Task 1 – Administration and Project Management |  |  |  |
| Project Manager – | 8 | $75.95 | $607.60 |
| Task 2 - Preliminary Design Structural |  |  |  |
| Project Engineer – | 57 | $59.94 | $3416.58 |
| Project Engineer – | 135 | $36.95 | $4988.25 |
| Project Engineer | 2 | $42.16 | $84.32 |
| Task 3 – Preliminary Design Roadway |  |  |  |
| Project Engineer | 16 | $51.08 | $817.28 |
|  | Total Direct Salaries Due this Invoice |  | $9,914.03 |

Section 3: Project Cost Breakdown

DIRECT COSTS-Sub-consultants & Other direct costs

| Task Description/Sub-consultant firm name (**Denotes DBE Sub) | AMOUNT |  |
| --- | --- | --- |
| SUB-CONSULTANT DIRECT COSTS |  |  |
| Task 1 – Surveying - ABC | $1,655.75 |  |
| Task 3 – Hydraulics – DEF (DBE Firm)** | $10,876.72 |  |
| OTHER DIRECT COSTS |  |  |
| Printing | $41.37 |  |
|  | Total Direct costs due this Invoice | $12,573.84 |

Section 4: Progress Report - % Complete & DBE

|  | Total Costs (includes Salaries, Sub-consultants & Direct Costs) |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Total Budgeted | Total Paid to Date | Percent Expended (Budgeted/Expended) | Estimate % Task Complete (Deliverables) |
| Task 1 - Administration and Project Management | $10,000 | $607.60 | 6.07% | 6% |
| Task 2 - Preliminary Design Structural | $57,532.47 | $8,489.15 | 14.76% | 15% |
| Task 3 - Preliminary Design Roadway | $53,367.53 | $817.28 | 1.5% | 3% |
| TOTAL | $120,900.00 | $9,914.03 | 22.33% | 24% |

| DBE Verification – Summary To Date |  |  |  |
| --- | --- | --- | --- |
| DBE Goal = 5% Consultant Contract Total = $120,900.00 DBE Target $ Amount = $6,045.00 |  |  |  |
| DBE Sub-Consultant | Subcontract Amount | Total $ Billed to Date | Overall DBE % Met to Date |
| DEF Engineering | $10,876.72 | $10,876.72 |  |
| Total DBE Contract $ | $10,876.72 |  |  |
| Total $ Billed to Date |  | $10,876.72 |  |
| Overall DBE % Met To Date = Total $ Billed to Date/DBE Target $ Amount |  |  | 100% |

Section 4: Progress Report – Narrative

Task 1 Administration and Project Management:  Completed progress reports.

Task 2 Preliminary Design Structural: Have billed 14.76% of preliminary structural plans to date.  Currently working on hydraulics report. Preliminary Structural Plans expected to be completed by July 1, 2012.

Task 3 Preliminary Design Roadway: Have billed 1.5% of preliminary roadway plans to date.  Currently working on initial roadway alignment. Preliminary Roadway Plans expected to be completed by July 1, 2012.