## Cover
MISSOURI DEPARTMENT OF TRANSPORTATION
Standard Inspection and Testing Plan (ITP): |  |  |  |  | Date Version: | June 2013
| Section 200 | Section 300 | Section 400 | Section 500 |  | Section 600 | Section 700
| Section 800 | Section 900 | Help and Instructions |  |  | Print Sec 200-900

## Help and Instructions
Go Back to Front
DIVISION 000:
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  | Acceptance Criteria
Spec. |  | Where the governing specifications are found.
Item Description |  | Most basic description of the element of work.
Parameter or Procedure |  | Describes which portion of the work item being discussed on this line of the ITP. It is common for a specification or item to have several parameters or procedures.
Additional Reference |  | contains useful information such as other specification sections that may be integral to inspection of the item.
Acceptance Criteria |  | Describes how the requirement is met for that parameter or procedure. These are mostly standardized and match the types in SiteManager.
Minimum Frequency
| Contractor QC |  | MoDOT QA
Contractor QC |  | Under MoDOT quality management, the contractor is responsible for 100% of quality control. The contractor may delegate to subs or suppliers, but must ensure they comply with the project ITP.
MoDOT QA |  | MoDOT will follow the quality assurance scheduled here.
The frequencies listed may be in "word format" such as ONCE PER DAY. When inputted into SiteManager, the frequency may be translated to a "number format" such as 1 per 500cy that roughly represents the "word format". In case of conflict between SiteManager and the ITP frequency, the ITP should govern.
QC Documents
|  | Checklist | Test Record | Misc. | Electronic Process
Checklist |  | Checklists have been developed as an aid for more complex inspection. Be aware that the checklist may not cover all aspects of inspection.
Test Records |  | Every material test taken should generate a test record.
Misc. |  | Miscellaneous documents can cover many different types of deliverables. See the ITP or specifications for more detail.
Electronic Process |  | Indicates that there is a specific process the contractor must comply with to allow MoDOT to collect data electronically. No deviations from this requirement should be allowed without headquarters approval.
The various documents required from QC will be stored in Sharepoint with the exception of ones with an electronic process developed.

## 200
DIVISION 200: Grading and Removals | [9 empty] | Minimum Frequency |  | QC Documents
[10 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  |  | Acceptance Criteria
Section 201: Clearing and Grubbing
201 | 0.2 | Clearing and Grubbing | Clearances, disposal, and finish | See Checklist | [5 empty] | 1 per Day |  | ²
Section 202: Removal of Roadways and Buildings
202 |  | Removal of Roadways and Buildings | Construction and Conformance Requirements | See Checklist | [5 empty] | 1 per Day |  | ²
Section 203: Roadway and Drainage Excavation, Embankment and Compaction
203 | .3 and .5 | Borrow Material | Soil Characteristics | Proctor and Plasticity Index |  |  |  |  | Certification and Testing | 1 per Soil Type | 1 per Borrow Area |  | ²
203 | .4.1 | Grade construction requirements
203 |  | Placement and compaction of Embankment | Density, Moisture, Thickness, Frozen | See Checklist |  | Density Test Required |  |  | Testing | 1 per Lift, per 500', per activity | 1 per Day | ² | ² |  |  | EPG 203.5
203 |  | Compaction of Cut | Density, Moisture, Thickness, Frozen | See Checklist |  | Density Test Required |  |  | Testing | 1 per Lift, per 500', per activity | 1 per Day | ² | ²
203 | 0.5 | Comp of Emb and Treatment of Cut Areas with Moisture & Density | Standard Compaction | AASHTO T99 or TM40 |  |  |  |  | Testing | 1 per Soil Type | 1 per Project |  | ²
203 | 0.5 | Comp of Emb and Treatment of Cut Areas with Moisture & Density | Moisture Correction Factor | TM 35 | Use with nuclear density |  |  |  | Testing | 1 per Soil Type | 1 per Day |  | ²
203 | .5.2 | Moisture Control | Plasticity Index | Class A , LL>40 within 5' of top of finished subgrade shall be compacted at no less than optimum |  |  |  | T89 | Testing | 1 per Soil Type | 1 per Day |  | ²
Section 204: Embankment Monitoring
204 | .10.3 | Embankment Monitoring | Settlement Gauge | Per Contract JSP |  |  |  |  | Visual | 1 per Day, or as per Contract | 1 per Week |  | ²
204 | .20.3 | Embankment Monitoring | Pore Pressure | Per Contract JSP |  |  |  |  | Visual | 1 per Day, or as per Contract | 1 per Week |  | ²
Section 205: Subgrade Stabilization
205 | 0.2 | Stabilization Material | Gradation | AASHTO T87 and T88 |  |  | EPG 205.2.2 |  | Testing | 1 per Project/ Gradation /Source | 1 per Project |  | ²
205 | 0.2 | Stabilization Material | Liquid Limit | T89 |  |  |  |  | Testing | 1 per Project/ Gradation /Source | 1 per Project |  | ²
205 | 0.2 | Stabilization Material | Plasticity Index | T90 |  |  |  |  | Testing | 1 per Project/ Gradation /Source | 1 per Project |  | ²
205 | 0.2 | Stabilization Material | Moisture Density Relation | T99 Method C |  |  |  |  | Testing | 1 per Project/ Soil Classification. | 1 per Project |  | ²
205 | 0.3 | Construction | Application Uniformity | Extends 18" each side of roadway. Proof rolling only if required by Engineer |  |  |  |  | Visual | 1 per Activity | 1 per Day | ²
Section 206: Structure Excavation
206 | 0.2 | Excavation for Footings and Culvert Floors | Depth and Keyways | See Checklist |  |  |  |  | Visual | 1 per Foundation |  | ²
206 | .3.2 | Excavation | Stabilization and Testing | Test Hole and Stabilization |  |  |  |  | Measurement | 1 per Foundation | 1 per Foundation | ²
206 | .4.6 | Excavation | Footing Drainage | See Checklist |  |  |  |  | Visual | 1 per Day |  | ²
206 | .4.7 | Excavation | Cofferdams | See Checklist |  |  |  |  | Measurement | 1 per Day |  | ²
206 | .4.8 | Excavation | Temporary Shoring | See Checklist |  |  |  |  | Measurement | 1 per Day |  | ²
206 | .4.9 | Excavation | Seal Courses | See Checklist |  |  |  |  | Measurement | 1 per Day |  | ²
206 | .4.10, | Backfill | Structure Fill; Footing Backfill | See Checklist |  |  |  |  | Visual / Testing | I per Lift |  | ²
206 | .4.11. | Porous Backfill | Construction | See Checklist |  |  |  |  | Visual | I per Lift |  | ²
206 | .4.11.1 | Porous Backfill | Material | Gradation and deleterious |  | Materials and gradation per Sec 1009 |  |  | Testing | I per 2000 Ton, 1 per Project min | 1 per Project |  | ²
206 | .4.12 | Flowable Fill | Mix Design | Approved Mix design. |  |  |  | Sec 621 | Document
Section 207: Linear Grading
207 | .2.1 | Class 1 and 2 for Mainline | Construction | See Checklist |  |  |  |  | Measurement | 1 per 10 Stations, 1 per Area Worked min |  | ²
207 | .2.1 | Class 1 and 2 for Shoulder | Construction | See Checklist |  |  |  |  | Measurement | 1 per 10 Stations, per shoulder, 1 per Area Worked min |  | ²
Section 208: Interception Ditch
208 | .2. | Interception Ditch | Construction | See Checklist |  |  |  |  | Visual | 1 per Area Worked |  | ²
Section 209: Subgrade Preparation
209 |  | Construction | Grade | See Checklist |  |  |  |  | Measurement | 1 per 100' |  | ²
209 |  | Construction | Uniformity, Moisture | See Checklist |  |  |  |  | Visual / Measurement | 1 per Day |  | ²
Section 210: Subgrade Compaction
210 | .2.1 | Subgrade Compaction | Construction | See Checklist |  | Density Test Required |  |  | Testing | 1 per 1000 Feet of Alternating Lanes. | 1 per Day | ² | ²
Section 211: Subgrade Scarifying
211 | 0.2 | Subgrade Scarifying | Construction | See Checklist |  | Performed in areas determined by Engineer |  |  | Visual | 1 per 1000 Feet of Alternating Lanes. |  | ²
Section 212: Subgrading & Shouldering
212 | .2.1. | Subgrading / Shouldering | Construction | See Checklist |  |  |  |  | Testing | 1 per Lift, per 500', per activity |  | ²
Section 214: Rock Fill
214 | 0.2 | Rock Fill | Construction and Materials | See Checklist |  | Uniformly graded suitable rock |  |  | Visual | 1 per Lift / Activity | 1 per Day | ² | ²
Section 215: Shaping Slopes
215 | 0.2 | Shaping Slopes | Construction | See Checklist |  |  |  |  | Visual / Measurement | 1 per 10 Stations |  | ²
Section 216: Removals for Bridge Structures
216 | .10.2 | Removal | Construction | See Checklist |  |  |  |  | Visual / measurement | 1 per Structure |  | ²
Note on A10: meyerm3: needs attention

## 300
DIVISION 300: Bases and Aggregate Surfaces | [8 empty] | Minimum Frequency |  | QC Documents
[9 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO FRONT
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  | Acceptance Criteria
Section 302: Stabilized Permeable Base
302 | .2.1 | Asphalt or Cement Stabilized Base | Material: Gradation Test & Deleterious |  |  |  | Sec 1009, T11, T27 | testing | 1 per 2000 Ton | 1 per project |  | ²
302 | .2.2 | Asphalt or Cement Stabilized Base | Construction | See Checklist |  |  |  | Visual | 1 per Day / Activity |  | ²
Section 303: Rock Base
303 | .2.2 and .2.3 | Rock Base | Material Quality and size. Section Thickness, and Compaction | See Checklist |  | Material report |  | Visual / Measurement | 1 per lift, per 500', per active grading spread/4 per day min EPG 203.5 | 1 per 10 QC | ² | ²
303 | .3.5 | Surface Material | top 2" Gradation | See Sec. 1007 |  |  |  | testing | 1 per 2000 ton | 1 per 8000 ton |  | ²
303 | .3.5 | Surface Material | top 2" PI | See Sec. 1007 |  |  |  | testing | 1 per 10,000 ton | 1 per 40,000 ton |  | ²
303 | .3.6 | Final Grade | Construction | See Checklist |  |  |  | measurement | 1 per 100'. | 1 per 1000' | ²
Section 304: Aggregate Base Course
304 | .2.3 | Placing | Subgrade and Measuring lift thickness | See Checklist |  |  | See Sec 209 | measurement | 1 per 1000 Ton, 1 per Day min | 1 per 4000 ton, 1 per Project min | ²
304 | .3.4 and .4.1 | Shaping and Compacting | >4" thickness Density | See Checklist |  |  | T191 or T310, TM 35, ASTM D6951 (DCP for Type 7 base) | visual / testing | 1 per 1000 Ton, 1 per Day min | 1 per 4000 ton, 1 per Project min | ² | ²
304 | .3.4 | Shaping and Compacting on shoulders | <4" thickness Density | See Checklist |  |  |  | visual | 1 per Day / Activity |  | ²
304 | .4.1 and .4.1.3 | Aggregate Base QC/QA | Section Thickness | measurement meets plans |  |  |  | measurement | 1 per 1000 Ton, 1 per Day min. | 1 per 4000 ton, 1 per Project min
304 | .4.1 | Aggregate Base >1000 Tons a Week | Gradation Test & Deleterious Material | T11, T27, & TM71 |  | See Sec 1007. testing is per source. QC retains samples |  | testing | 1 per 2000 Ton, 1 per Day min. | 1 per 8000 Ton, 1 per Project min |  | ²
304 | .4.1 | Aggregate Base <1000 Tons a Week | Gradation Test & Deleterious Material | T11, T27, & TM71 |  | See Sec 1007. testing is per source. QC retains samples |  | testing | 1 per 250 Ton, 1 per Week min. | 1 per 8000 Ton, 1 per Project min |  | ²
304 | .4.1 | Aggregate Base <1000 Tons a Week | Retained Samples for Gradation Test & Deleterious Material | T11, T27, & TM71 |  | See Sec 1007. testing is per source. |  | testing | NA | 1 per Project min 1 per Week at least 1 per 16,000 Ton
304 | .4.1 | Aggregate Base QC/QA | Plasticity Index | T89 & T90 | See Sec 1007. testing is per source. QC retains samples |  |  | testing | 1 per 10000 Ton, 1 per Project min. | 1 per 40,000 Ton, 1 per Project min. |  | ²
304 | .4.1 | Aggregate Base QC/QA | Retained Samples for Plasticity Index | T89 & T90 | See Sec 1007. testing is per source. QC retains samples |  |  | testing | NA | 1 per Week at least 1 per 80,000 Tons
304 | .4.2 | Aggregate Base QC/QA | Standard Compaction | T 99, Method C |  | ASTM D6951 (DCP for Type 7 base) |  | testing | 1 per source or material change | 1 per source or material change |  | ²
Section 310: Aggregate Surface
310 | 0.2 | Aggregate Surface < 500 Tons | Gradation & Deleterious | AASHTO T27, T11, TM71 |  |  | Spec Reference 1006 | Certification | 1 per activity | 1 per activity |  | ²
310 | 0.2 | Aggregate Surface > 500 Tons | Gradation & Deleterious | AASHTO T27, T11, TM71 |  |  | Spec Reference 1006 | Testing | 1 per 2000 ton, 1 per Project min | 1 per 10000 Ton, 1 per Project min |  | ²

## 400
DIVISION 400: Flexible Pavements | [9 empty] | Minimum Frequency |  | QC Documents
[10 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  |  | Acceptance Criteria | [6 empty] | EPG
Section 401: Bituminous Base and Pavement
401 | .5. and .9. | Aggregate Gradation & Deleterious Content Control and %AC | QA Independent Samples | T11, T27, TM 71 |  |  | Only applies for greater than 500 tons per day |  | testing | na | 1 per Day
401 | .5. and .8. and .9. | Aggregate Gradation Control | QC/QA Split Samples | T11, T27, TM 71 |  | Split samples within 5% of QC |  |  | testing | 1 per 1000 Ton, 1 per Day min | 1 per 5 Days, 1 per Project min |  | ² | 0 |  | 401.2.4 460.3.15.1
401 | 0.5 | Deleterious Content Control | QC/QA Split Samples | T11, T27, TM 71 |  | Split samples within 5% of QC |  |  | testing | 1 per 1000 Ton, 1 per Day min | 1 per 5 Days, 1 per Project min |  | ²
401 | 0.5 | Binder Content | QC/QA Split Samples | T164, TM54, T287, T308 |  |  | Asphalt Content |  | testing | 1 per 1000 Ton, 1 per Day min | 1 per 5 Days, 1 per Project min |  | ²
401 | 0.5 | Recycled Asphalt Material (RAP) | Gradation and AC Content | T27, T164, T308 |  | extraction, binder ignition. QC retains split samples |  |  | testing | 1 per Day | 1 per Project |  | ² |  |  | 401.2.4
401 | .2.1 | Aggregate properties | Plasticity Index and Moisture Susceptibility | T89 and T90, and T283 |  | Additional testing if above design on fractions >10% passing #30 sieve |  |  | testing | 1 per mix | na |  | ² | 0 |  | 401.4.5
401 | .5.4 | Moisture Control | Moisture Content | T329 |  | Testing. Same Time as AC Content. Test any time moisture content changes. |  |  | testing | 1 at project start up and 1 per Week | 1 per Week, 1 per Project min |  | ² |  |  | 460.3.14.4
401 | .7.1 | Subgrade preparations | Roadway | See Checklist |  | TM20, Sec 209, Sec 407, Sec 408 |  |  | Visual / measurement | 1 at start of day, 4 per day min | 1 per Day | ² |  | 0 |  | 401.2.6
401 | .4.2 | Temperature limitations | Mixture Testing | TM20 | Binder and Mix temperatures |  |  |  | measurement | 4 per Day | 1 per Project | ² |  |  |  | 460.3.8, 1015
401 | .7.8 and .8.4. | Pavement Density and thickness | Coring of lifts | Core locations by random #s. |  | TM41 / T166 |  |  | Testing | 4 per Day | 1 per Week, 1 per Project min | ² | ² |  |  | 401.2.6
401 | .7.6 and .8.4 | Pavement Joints | Density | TM41 / T166 |  |  |  |  | testing | 1 per Activity | na | ² | ² | 0 |  | 401.2.6
401 | .10. | Surface Tolerance | Smoothness | TM 59, Sec 610 | Test prior to opening. |  |  |  | Testing | na | 1 per Activity | ² |  |  |  | .10.
401 | .12. | Pavement Marking | Visibility | TM80, Sec 620 | Test prior to opening. |  |  |  | Testing | na | 1 per Activity | ² |  |  |  | 0.1
Section 402: Bituminous Surface Leveling
402 | .2.3 | Recycled Asphalt Material (RAP) | RAP Gradation, AC content & Delt | T27, T164, T308, Sec 1004 |  |  | extraction, binder ignition |  | testing | 1 per Day | na |  | ² |  |  | 402.2.3 460.3.11
402 | 0.5 | Aggregate gradation and deleterious control | QC/QA Split Sample | T11, T27 & TM 71, Sec 1004.2 |  |  |  |  | testing | 1 per Day | 1 per 15000 tons |  | ² | 0 |  | 402.2.4
402 | 0.5 | Aggregate gradation and deleterious control | QA Independent Samples | T11, T27 & TM 71, Sec 1004.2 |  |  |  |  | testing | na | 1 per 10000 tons |  | ²
402 | .5. | Aggregate properties | Plasticity Index and Moisture Susceptibility | T89 and T90, and T283 |  | Additional testing if above design on fractions >10% passing #30 sieve |  |  | testing | 1 per mix | na |  | ² | 0 |  | 402.2.2
402 | 0.5 | % Asphalt Content (Binder) > 5000 tons | Mixture AC content | Determine using oil and plant tickets |  |  |  |  | measurement | 1 per activity | 1 per project |  | ²
402 | 0.5 | % Asphalt Content (Binder) > 5000 tons | Asphalt QA Verification | T164, TM54, T287, T308 |  |  | calculation or testing |  | testing | na | 1 per 10000 tons
402 | 0.7 | Moisture Control > 100 Tons | Moisture Content | T329 |  |  |  |  | testing | 1 per Day | 1 per Week, 1 per Project min |  | ² |  |  | 402.2.6 460.3.14.4
402 |  | Plant Temperature | Mixture Testing | TM20 | Binder and Mix temperatures |  |  |  | measurement | 4 per Day | 1 per Project | ² |  |  |  | 460.3.8, 1015
402 | .10.3 | Construction | Preparations, Hauling, Spreading, Compaction. | See Checklist |  |  |  |  | Visual / Measurement | 1 per Activity/Day |  | ²
Section 403: Asphaltic Concrete Pavement
403 | .5.1, .19.3. | Gradation and Deleterious Content Control | QC/QA Split Sample | T 27 & T 11 | QC retained samples 1 per week by QA |  |  |  | testing | 2 per Lot | 1 per Lot |  | ² |  |  | 403.1.5
403 | .5.2, .15.4 .19.3 | Mat Density | Pavement Testing | T 166 |  | By Random # |  |  | testing | 1 per Sublot | 1 per Lot |  | ² | 0 |  | 403.1.5
403 | .5.3, .19.3 | Mixture Testing | Asphalt content | AASHTO T 164, TM 54, T 287, T 308 |  |  |  |  | testing | 1 per Sublot | 1 per Lot |  | ² | 0 |  | 403.1.5
403 | .5.4, .19.3 | Mixture Testing | Voids in Min Aggr | VMA T 312 and R 35 |  |  |  |  | testing | 1 per Sublot | 1 per Lot |  | ² | 0 |  | 403.1.5
403 | .5.5, .19.3 | Mixture Testing | Air Voids | Va T 312 and R 35 |  |  |  |  | testing | 1 per Sublot | 1 per Lot |  | ² | 0 |  | 403.1.5
403 | .5.6., .19.3 | Mixture Testing | Tensile Strength Ratio | TSR of the mixture T 283 |  |  |  |  | testing | 1 per 10,000 Ton | 1 per 50,000 Tons, 1 per Project min |  | ² | 0 |  | 403.1.5
403 | .5.7., .19.3 | Mixture Testing | Aggregate properties | FAA, CAA, clay content, and thin and elongated particles |  |  | AASHTO T304, ASTM D5821, AASHTO T176 & ASTM D 4791 |  | testing | 1 per 10,000 Ton | 1 per Project |  | ² | 0 |  | 403.1.5
403 | .5.9. | Mixture Testing | Moisture Control | Moisture Content |  | T329 Testing. Same time as AC content |  |  | testing | start up and 1 per Week or if moisture changes | 1 per Week, 1 per Project min |  | ² |  |  | 403.1.5 460.3.14.4
403 | 0.12. | Surface Prep | Tack application and Weather Limitations | See Checklist |  | Prior to Placement |  |  | Visual / measurement | 1 per Day |  | ² |  |  |  | 403.1.12
403 | .15. | Pavement Density | Coring of lifts | Core locations by random #s. |  | TM41 / T166 |  |  | Measurement | 1 per Sublot | 1 per Lot | ² |  |  |  | 403.1.15
403 | .19.3 | Plant Temperature | Mixture Testing | TM20 | Binder and Mix temperatures |  |  |  | Measurement | 1 per Sublot | 1 per Day | ² |  | 0
403 | .16.1., .19.3 | Pavement Testing | Unconfined Joints | T 166 |  | By Random # |  |  | Testing | 1 per Sublot | 1 per Lot |  | ² | 0 |  | 403.1.16
403 | .19.3 | Mixture Testing | AC content of RAP | AASHTO T 164 |  |  |  |  | Testing | 1 per Lot | 1 per Project |  | ² | 0
403 | .19.3 | Mixture Testing | Voids Filled with Asphalt | VFA T 312 and R 35 |  |  |  |  | Testing | 1 per sublot | 1 per Lot |  | ² | 0
403 | .19.3 | Mixture Testing | Rice Test - Gmm | T 209 | Absorption > than 2.0 % run a Dry-back test |  |  |  | Testing | 1 per sublot | 1 per Lot |  | ² | 0 |  | 403.1.19
403 | .20.1 | Pavement Testing | Straightedging |  |  |  | 1/8" within 10' |  | Visual | prior to opening | verify QC | ²
403 | .22.4.1 | Lift Thickness | Average thickness of Density Cores | See Checklist |  |  | T148 |  | measurement | 1 per Lot | 1 per Lot | ²
403 | .22.4.1 | Full Depth Pavement Thickness | Roadway | See Checklist |  |  | T148 |  | measurement | 1 core per 1000' | verify QC 1 per Lot | ²
Section 407: Tack Coat
407 | .2. | Material |  | Emulsified Asphalt |  |  |  | Sect 1015 | certification | 1 per Delivery | 1 per Project |  | ² |  |  | 407.1.1
407 | .4.1. | Construction | Surface Prep, Application | See Checklist |  |  |  |  | Visual | 1 per activity |  | ² |  |  |  | 407.1.4
Section 408: Prime Coat
408 | .2. | Material |  | Type RC and MC Liquid Asphalt |  |  |  | Sec 1015 | certification | 1 per Delivery | 1 per Project |  | ² |  |  | 408.1.2
408 | .4.1. | Construction | Surface Prep, Application | See Checklist |  |  |  |  | Visual | 1 per activity |  | ² |  |  |  | 408.1.4
Section 409: Seal Coat
409 | 0.2 | Material | Aggregate gradation and deleterious control | T11, T27 & TM 71 |  |  |  | Sec 1003 | Documentation | 1 per activity | 1 per job |  | ² |  |  | 409.2.2
409 | .2.2 | Material | Asphalt Binder | ASTM D5, AASHTO T301 |  |  |  |  | Certification | 1 per shipment | 1 per job |  | ²
409 | .2.3, .5.3.2 | Material | Pre-coating | T164, TM54, T287, T308 |  | Sec 1015 |  | min. 0.5 %, | testing | 1 per activity | 1 per job |  | ²
409 | .3.2. | Construction | Mix, Equipment, and Weather | See Checklist |  | Per Mix Design |  |  | visual | 1 per Day |  | ² |  |  |  | 3.2
Section 413: Surface Treatment
413 | .10.2.1 , .20.2 | Microsurfacing and Scrub Seals | Aggregate Gradation Content Control | T 27 & T 11 |  |  | Provide Documentation prior to construction including job mix formula |  | Documentation | 1 per Day | 1 per Activity | ² | ² |  |  | 413.1 413.3
413 | 0..10, .20 | Microsurfacing and Scrub Seals | Equipment and Test Review | See Checklist |  | See checklist for microsurfacing and scrub seal |  |  | visual | 1 per mix |  | ² |  |  |  | 413.1
413 | .10.5, .20.4 | Microsurfacing and Scrub Seals | Surface conditions ,weather limits and roadway prep. | See Checklist |  | See checklist for microsurfacing and scrub seal |  |  | Visual | 1 per day |  | ² |  |  |  | 413.2
413 |  | Microsurfacing and Scrub Seals | Material - Emulsified Asphalt | [5 empty] | certification | 1 per shipment | 1 per project |  | ²
413 | .30.4.2, .30.6.1.2 | UBAWS | Aggregate Gradation and Deleterious QC/QA Split Samples | T 27, T11, and TM 71 | Sec 413.30.6, 413.30.7 |  |  |  | testing | 1 per 600 Ton | 1 per week |  | ² |  |  | 413.3.1
413 | .30.2. | UBAWS | Aggregate Gradation Content Control QA Independent Samples | T 27, T11 | Sec 413.30.6, 413.30.7 |  |  |  | testing | NA | 1 per Day |  | ²
413 | .30.5.1 | UBAWS | Weather limitations and Surface Condition and mix temperature | See Checklist |  |  |  |  | visual / measurement | 1 per Day |  | ²
413 | .30.5.4 | UBAWS | Membrane Application Rate | See Checklist |  |  | Polymer Modified Sec 1015 |  | measurement | 1 per Day | 1 per Week | ² | ² |  |  | 413.3.3
413 | .30.6.1.2 | UBAWS | Asphalt content QC/QA Split Samples | AASHTO T 287, T 308 |  |  |  |  | testing | 1 per 600 Ton | 1 per week |  | ²
413 | .30.6.1.2 | UBAWS | Asphalt content QA Independent Samples | AASHTO T 287, T 308 |  |  |  |  | testing | na | 1 per Day |  | ²
413 | .40.2 | Fog Sealing | Emulsified Asphalt | Sec 1015 | SS-1, SS-1H, CSS-1, CSS-1H |  |  |  | Documentation | 1 per day | 1 per Day |  | ² |  |  | 413.4
413 | .40.3 | Fog Sealing | Surface Preparation and tack application, | See Checklist |  |  |  |  | visual / documentation | 1 per activity |  | ² |  |  |  | 413.4
413 | .50, .60, .70, .80 | Crack Sealing and Crack Filling | Material | M 324, Sec 1057, Sec 1015 |  |  |  |  | PAL / Certification | 1 per shipment | 1 per Project |  | ² |  |  | 413.5
413 | .50, .60, .70, .80 | Crack Sealing and Crack Filling | Surface Preparation and weather limitations | See Checklist |  |  |  |  | visual | 1 per Day |  | ²

## 500
DIVISION 500: Rigid Pavements | [8 empty] | Minimum Frequency |  | QC Documents
[9 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  | Acceptance Criteria
Section 501: Concrete
501 | .2.1 | Aggregate | QC and QC/QA Split samples Gradations, Deleterious, and Absorptions | T27 and T11, TM 71, T85 |  | 1005 |  | testing | 1 per 500 CY | 1 per 2500 CY, 1 per project min |  | ²
501 | .2.1 | Aggregate >500 cy | QA Independent samples Gradations, Deleterious, and Absorptions | T27 and T11, TM 71, T85 |  | 1005 |  | testing | na | 1 per Project |  | ²
501 | .2.1 | Aggregate | Thin or Elongated Pieces | ASTM D4791 |  |  |  | testing | 1 per source/year | 1 per source/year |  | ²
501 | .3.8 | Consistency | Compressive Strength Requirement, Slump and Air | T22 T119 T152, |  |  |  | testing | 1 per 100 CY per day per mix | 1 per 500 CY, 1 per Structure Min |  | ²
501 | 0.5 | Consistency | Concrete Small Quantities |  |  |  |  | visual / certification | 1 per activity | 1 per project |  | ²
501 | .3.8 | Mix Design Verification | 28 day cured Cylinders | T22 T23 |  |  |  | Field Testing | 1 per 500 CY, 1 per Mix Design min | 1 per Mix Design |  | ²
501 | .6.3 | Concrete Plant | Calibrations | Calibrated and Certified Annually |  |  |  | Document | 1 per Year | 1 per Plant | ²
501 | .6.3 | Concrete Plant | Verifications | Verify |  |  |  | Document | 1 per 30 Working Days | 1 per Plant | ²
501 | .6.3 | Concrete Plant | Mixing and Delivery | See checklist |  |  |  | Measurement / Check | 1 per pour |  | ²
501 | .8.2 | Concrete | Uniformity Testing | See Checklist | [6 empty] | ² |  | ²
501 | .11. | Concrete Components | Admixtures | Approval required prior to use |  | Sec 1054 |  | PAL | 1 per shipment | 1 per Project |  | ²
501 | .14. | Concrete Components | Cementitious Material | Approval required prior to use | Ternary mixes allowed for all classes |  |  | Document | 1 per shipment | 1 per Project |  | ²
501 | .14. | Concrete Components | Tinting Material | Approval required prior to use | Sec 1056 |  |  | Document | 1 per shipment | 1 per Project |  | ²
501 | .14.6 | Concrete Components | Mixing water from non-potable source | Approval required prior to use |  |  |  | testing | 1 per source | 1 per Project |  | ²
Section 502: Concrete Base and Pavement
502 | .4. | Construction | Surface Preparation, placing and finishing | See Checklist |  |  |  | visual / measurement | 1 per Day |  | ²
502 | .5. | Construction | Joints | See Checklist |  |  |  | visual | 1 per activity |  | ²
502 | .6. | Construction | Curing | See Checklist | Sec 1055 PAL |  |  | PAL / Visual | 1 per Activity |  | ² | ²
502 | .7. | Construction | Formwork | See Checklist |  |  |  | Visual | 1 per Activity |  | ²
502 | .8. | Construction | Surface Smoothness | See Checklist | Sec 610 |  |  | Documentation | 1 per Project | 1 per Project | ²
502 | .9. | Construction | Opening to Traffic | See Checklist |  |  |  | documentation | 1 per activity |  | ²
502 | 0.10. | Placement | Cores for Thickness and Strength | T24, T22, T231 T148 |  |  |  | Testing | 1 per Sublot | 1 per Lot | ² | ²
502 | .11.2.1.1 | Material | Aggregate Gradations | T27, T11 |  |  |  | Testing | 1 per Week | 1 per Project |  | ²
502 | .11.2.1.2 | Materials | Aggregate Deleterious | TM71 |  |  |  | Testing | 1 per 7500 SY, 1 per Day min | 1 per Week |  | ²
502 | .11.2.1.3 | Materials | Coarse Aggregate Absorptions | Absorption of Coarse Aggregate |  |  | T85 | Testing | 1 per 2000 CY | 1 per 10,000 CY |  | ²
502 | .11.2.1.4 | Materials | Coarse Aggregate Thin and Elongated | ASTM D4791 |  |  | + 3/4" | Testing | 1 per 10,000 CY | 1 per Project |  | ²
502 | .11.2.2, .11.3.3 | Concrete Consistency | Slump | T119 |  |  |  | Testing | 1 per 500 Cy, 1 per Day min | 1 per Day | ² | ²
502 | .11.2.3, .11.3.3 | Concrete Consistency | Air Content | T152 |  | By random # |  | Testing | 1 per 500 Cy, 1 per Day min | 1 per Day | ² | ²
502 | .11.5 | Placement < 8" | Pavement Thickness | stick readings |  | random location |  | Measurement | 1 per 7500 SY | 1 per 30000 SY |  | ²
Section 503: Approach Slab
503 | .2. | Material | Concrete | Paving or B1 concrete |  |  |  | testing | Sec 501 | Sec 501 |  | ²
503 | .3. | Material | Aggregate Base | density and material |  |  | 1007 | testing/ visual | Sec 304 | Sec 304 |  | ²
503 | .3. | Construction | Placement | See Checklist | Sec 703, Sec 706, Sec 502, Sec 1055 |  |  | visual | 1 per activity |  | ²
Section 504: Concrete Approach Pavement
504 | .2. | Material | Concrete | Paving or B1 concrete |  |  |  | testing | Sec 501 | Sec 501 |  | ²
504 | .3. | Material | Aggregate Base | density and material |  |  | 1007 | testing/ visual | Sec 304 | Sec 304 |  | ²
504 | .3. | Construction | Placement | See Checklist | Sec 304, Sec 503, Sec 609 |  |  | visual | 1 per activity |  | ²
Section 505: Bridge Deck Concrete Wearing Surface
505 | .10, .20, .30., .40. | Material | Concrete Mixture and Components | See 501 |  |  |  | 1005 | Sec 501 | Sec 501 |  | ²
505 | .10, .20, .30., .40. | Consistency | Slump, Air Content, Unit Weight | ASSHTO T119 T152 and T121 |  |  |  | Testing | 1 per 2 Hours | 1 per day | ² | ²
505 | .10, .20, .30., .40. | Design Verification | 28 day cured Cylinders | T22,T23 |  | 28 Day Cure |  | Testing | 1 per 500 YD / Mix | 1 per project |  | ²
505 | .10, .20, .30., .40. | Construction | Compressive Strength Requirement | T22,T23 |  |  | Field Cure | Testing | 1 per pour | 1 per project |  | ²
505 | .10, .20, .30., .40. | In Place Density | Density | Modot TM 36 |  |  |  | Testing | 1 per 100 SY, 3 per Continuous Pour Min | 1 per activity |  | ²
505 | .10, .20, .30., .40. | Construction | Placement | See Inspection Checklist |  |  |  | visual / measurement | 1 per pour |  | ²
Section 506: Concrete Overlays for Pavements
506 | .20. , .30. | Materials | Concrete Mixture and Components |  |  | See 502 |  | Testing | Sec 502 | Sec 502 |  | ²
506 | .20. , .30. | Construction | Placement, Joints, Curing, Formwork, Smoothness, and Opening to Traffic | See Inspection Checklist |  |  |  | visual / measurement | Sec 502 |  | ²
506 | 0.10. | Placement | Cores for Thickness and Strength | See Inspection Checklist |  |  |  | Testing | Sec 502 | Sec 502 | ² | ²
506 | .11.2.2, .11.3.3 | Concrete Consistency | Air and Slump | See Inspection Checklist |  |  |  | Testing | Sec 502 | Sec 502 | ² | ²
506 | .20. | Materials | Interlayer |  |  |  |  | Documentation | 1 per activity | 1 per project |  | ²
506 | .20. | Placement | Interlayer | See Inspection Checklist |  |  |  | Visual | 1 per activity |  | ²
506 | .20. | Construction | Profile | Establish field profile |  |  |  | Document | 1 per project |  |  |  | ²
Section 507: Strength of Concrete using Maturity Method
507 | .1. | Construction | Profile | Provide necessary information if used |  |  |  | Document | 1 per project |  |  |  | ²

## 600
DIVISION 600: Incidental Construction | [9 empty] | Minimum Frequency |  | QC Documents
[10 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  |  | Acceptance Criteria
Section 602: Markers
602 | .2.1 | Materials | Coating, Weight, Dimensions, Mill Tests |  |  |  |  | Per 1044 | Certification/ Testing | 1 per Shipment | 1 per project |  | ²
602 | 0.3 | Construction |  | See Checklist |  |  | Posts driven as per Section 903 |  | Visual | 1 per Day /Installation |  | ²
Section 603: Water Line Installation
603 | 0.2 | Materials |  | Pipe and appurtenances as per the appropriate AWWA specification |  |  | QA is usually by utility |  | Certification | 1 per Installation | 1 per Installation |  | ²
603 | 0.2 | Construction Requirements |  | See Checklist if MoDOT inspected |  | Backfill per Sec 726, Concrete per Sec 501 |  |  | Document | 1 per Activity |  | ²
Section 604: Miscellaneous Drainage
604 | .10.2 | Materials | Precast Misc. Drainage Items |  |  |  |  | Sec 1033 | Document | 1 per Shipment | 1 per project |  | ²
604 | .10.2 | Materials | Reinforcing Steel, Curing Compounds, joint materials | Sec 1036 and 1055 and 1057 |  |  |  |  | PAL | 1 per Shipment | 1 per project |  | ²
604 | .10.2 .40.2 | Materials | Concrete for CIP | Class B, See Sec 501 and Sec 703. |  |  |  |  | Visual/ Testing | 1 per Day /Activity | 1 per Activity |  | ²
604 | .10.3.1 | Construction | Misc Drainage items and methods | See Checklist |  | Sec 706, 206, 1030, 726, 501 |  |  | Visual | 1 per Day /Activity | 1 per project | ²
604 | .30.2 | Materials | Mortar and vitrified clay sewer pipe | Sec 1030, 1066 |  |  |  |  | Document/ QPL | 1 per shipment | 1 per project |  | ²
604 | .60.2 | Materials | Slotted Drains | See Sec 1051 |  | Per standard drawing 604.70 |  |  | Visual / Testing | 1 per Day /Activity | 1 per project |  | ²
604 | .60.3.2 | Construction Slotted Drains | Orientation and Bedding | See Checklist |  |  |  | 726, 609.10, 1051 | Visual / Testing | 1 per Day /Activity |  | ²
Section 605: Underdrainage
605 | 0.2 | Materials | Aggregates | 1009, |  |  | Porous Backfill T27 |  | Testing | 1 per Activity | 1 per project |  | ²
605 | 0.2 | Materials | Geotextile and Geocomposite Drainage | 1011, 1012, |  |  | Types per plan |  | Documents | 1 per Activity | 1 per project |  | ²
605 | 0.2 | Materials | Pipe and Rodent Guards | 1013, 1022, 1025 |  |  | Types per plan |  | Documents | 1 per shipment | 1 per project |  | ²
605 |  | Construction | Misc Underdrainage | See Checklist |  | See Sec 203, 501, 605.6, 1013 and Standard Drawings 605.x |  |  | Visual | 1 per Activity |  | ²
605 |  | materials | Concrete for CIP | See 501 |  |  |  |  | Testing | 1 per Activity | 1 per project |  | ²
Section 606: Guardrail, Crashworthy End Terminals, One-Strand Access Restraint Cable and Three-Strand Guard Cable
606 | 0.2 | Materials | Guardrail, Crashworthy End Sections and Guard Cable | Sec 1040, 1065 |  |  |  |  | QPL / Testing | 1 per Shipment | 1 per project |  | ²
606 | .2. , .2.1 , .2.2 | Materials | Concrete | Sec 501 |  | Concrete place per 703 and Cold Weather Plan |  |  | Testing | 1 per Installation | 1 per Installation |  | ²
606 | .3.1 | Construction | Guardrail, End Treatments, Cables | See Checklist |  | Sec 502, 703, 1080, 1065, and Standard Drawings 606.x |  |  | Visual | 1 per Day /Installation |  | ²
606 | .3.1.2 | Construction | Slope Requirements | See Checklist |  |  |  |  | Measurement | 1 per Day /Installation |  | ²
Section 607: Fencing
607 | .10.2 | Materials | Chain Link and woven wire and posts | Per 1043 and 1050 |  |  |  |  | Documentation | 1 per shipment | 1 per shipment |  | ²
607 | .10.2 | Materials | Concrete | Concrete class B or Commercial per 501 |  |  |  |  | Testing/ Certification | 1 per Activity | 1 per project |  | ²
607 |  | Construction | Chain Link and woven wire fencing | See Checklist |  | See Sec 501, 903.3.1.2 and Standard Drawing 607.x |  |  | Visual | 1 per Day /Installation |  | ²
Section 608: Concrete Median, Median Strip, Sidewalk, Curb Ramps, Steps and Paved Approaches
608 | 0.2 | Materials | Epoxy, Truncated Domes, | 1039, 1067 |  |  |  |  | QPL | 1 per Delivery | 1 per project |  | ²
608 |  | Materials | Concrete | Sec 501 |  | Concrete place per 703 and Cold Weather Plan |  |  | Testing | 1 per Day/Activity | 1 per activity |  | ²
608 |  | Materials | Reinforcing Steel, Curing Compounds, joint materials | 1036, 1057, 1055 |  |  |  |  | PAL | 1 per shipment | 1 per project |  | ²
608 |  | Materials | Concrete Tint | 1056 |  |  |  |  | Certification | 1 per Installation | 1 per project |  | ²
608 | .3.1 | Construction | Misc | See Checklist |  | Sec 209, 502, 703, 706, and Standard Drawings 608.x |  |  | Visual | 1 per Day /Installation |  | ²
Section 609: Paved Drainage
609 | .10.2 | Materials | Concrete | Sec 501 |  | Class B or Pavement Concrete per 501 |  |  | testing | 1 per Day | 1 per Activity |  | ²
609 | .10.2 | Materials | Reinforcing Steel, Curing Compounds, joint materials | 1036, 1057, 1055 |  |  |  |  | PAL | 1 per Delivery | 1 per project |  | ²
609 | .30.2, .30.3 | Materials | Asphalt Curbs | 1002, 1015 | 401, 403 |  |  |  | Testing | 1 per Day /Installation | 1 per project |  | ²
609 | .10.3.1, .10.3.4 | Construction | Curbs, Gutters, and Drain Basins | See Checklist |  | See Sec 401, 403, 502, 604, 703, 725, Standard Drawing 609.x |  |  | Visual | 1 per Day /Installation |  | ²
609 | .10.3.1 | Construction | Rock Ditch Liner | See Checklist |  | Standard Drawing 609.x |  |  | Visual | 1 per Day /Installation |  | ²
609 | .40.2 | Materials | Drain Basin | 609.60, 614, 1020, 1033 |  | Certifications and approved products |  |  | Approved Materials | 1 per Day /Installation | 1 per Activity |  | ²
609 |  | Materials | Geotextile | Sec 1011 |  |  |  |  | PQL / Certification | 1 per Activity | 1 per project |  | ²
609 | .70.2, .70.3 | Materials | Bedding and Rock Liner | Sec 611 |  |  |  |  | Visual | 1 per Activity | 1 per project |  | ²
Section 610: Pavement Smoothness
610 | .10.1 | Description | Pavement Smoothness | See Checklist |  | See Sec 401, 403, 502, 506, |  |  | Testing | 1 per Day /Installation |  | ²
610 | 0.2 | Materials | Pavement Smoothness | AASHTO M 328 |  | MoDOT TM-59 |  |  | Testing | 1 per Day /Installation | 10% of QC |  |  | ²
610 | 0.4 | Construction | Pavement Smoothness | See Checklist |  | Sec 610 |  |  | Testing | 1 per Day /Installation |  | ²
Section 611: Embankment Protection
611 | .30.2 | Materials | Rock | [5 empty] | Visual | 1 per day | 1 per Activity |  | ²
611 | .30.2 | Materials | Concrete for Slope Projection | Class B per 501 |  | See Sec 703 |  |  | testing / certification | 1 per Activity | 1 per project |  | ²
611 | .30.2 | Materials | Curing Compounds | Sec 1055 |  |  |  |  | PAL | 1 per shipment | 1 per project |  | ²
611 | .30.3 | Construction | Rock Blanket, Revetment, Concrete Slope Protection | See Checklist |  | See Sec 501, 703, Standard Drawing 611.x |  |  | Visual | 1 per Day /Activity |  | ²
611 | .30.3 | Construction | Gabion Wall | See Checklist |  | per plan |  |  | Visual | 1 per Day /Activity |  | ²
611 | .30.2 | Materials | Gabion Baskets and rock |  |  | per plan |  |  | Certification / visual | 1 per Day /Activity | 1 per project |  | ²
Section 612: Impact Attenuators
612 | .2.2, .2.3 | Materials | Sand Barrels, TMAs | FS-612 Table 1 of Prequalified List, 1005, 1042, 1063 |  | Per MUTCD with manufacturer's certification NCHRP 350 |  |  | Certification | 1 per Shipment | 1 per project |  | ²
612 | .4.1 | Construction | Sand Barrels | See Checklist |  |  | Standard Drawing 612.x |  | Visual | 1 per Day |  | ²
Section 613: Pavement Repairs
613 | 0.2 | Materials | Concrete | 502, |  |  |  |  | testing / certification | 1 per Day /Installation | 1 per project |  | ²
613 | 0.2 | Materials | Epoxy | 1039 |  |  |  |  | PQL | 1 per Installation | 1 per project |  | ²
613 | 0.2 | Materials | Curing Compounds, Dowel Bars, and Joint Materials | 1055, 1057 |  |  |  |  | PAL | 1 per shipment | 1 per project |  | ²
613 | .3, .10 | Construction | Full Depth and Partial Repairs | See Checklist |  | Sec 202, 210, 304, 502, 622, 623, Standard Drawing 613.x |  |  | visual | 1 per day |  | ²
613 |  | Construction | Dowel Bar Retrofit and Cross-stitching | See Checklist |  | See plan and Standard Drawing 613.x |  |  | visual | 1 per day |  | ²
613 |  | Materials for Dowel Bar Retrofit and Cross-stitching | Rapid Setting Concrete | Approval per Engineer |  |  | Epoxy see Sec 1039 |  | certification | 1 per installation | 1 per project |  | ²
Section 614: Drainage Fittings
614 | .20.2 | Material | misc | See Standard Drawing 614.x |  | Automatic floodgates either per plan or per levee district. |  |  | certification | 1 per Delivery | 1 per project |  | ²
614 | .30.3 | Construction | Misc. | See Checklist |  | See Standard Drawing 614.x |  |  | Visual | 1 per Day /Installation |  | ²
Section 616: Temporary Traffic Control
616 |  | Material | misc | See Sec 1063 and MUTCD |  | NCHRP350 compliance |  |  | certification | 1 per Delivery | 1 per project |  | ²
616 |  | Construction | Misc. | See Checklist |  | Sec 107.5, 902, Plans and TCP |  |  | Visual | 1 per Day /Installation |  | ²
Section 617: Concrete Traffic Barrier
617 | .10.2 | Materials | Rebar, Curing Compounds, Dowel Bars, and Joint Materials | Sec 1036, 1055, 1057. |  |  |  |  | PAL | 1 per Shipment | 1 per project |  | ²
617 | .10.2 | Materials | Delineators, Prestressing Strands | Sec 1065, AASHTO M 203 |  |  |  |  | Certification | 1 per Shipment | 1 per project |  | ²
617 | .10.3.1 | Materials | Concrete | B / air or B1 / air 4,000 psi |  |  |  | Section 501 | Testing | 1 per day | 1 per activity |  | ²
|  | Materials | Precast Temporary Barrier | Sec 1064 |  |  |  |  | Certification | 1 per shipment | 1 per project |  | ²
617 | .10.3.1 | Construction | Temporary and Permanent Concrete Barrier | See Checklist |  | Section 501, 502, 703, Standard drawing 617.x |  |  | Visual | 1 per installation |  | ²
Section 619: Pavement Edge Treatment
619 | 0.2 | Material | Misc. Granular | Approved material |  |  |  |  | Visual | 1 per Installation | 1 per project |  | ²
619 | 0.3 | Construction | Edge Treatment | See Checklist |  |  | Standard Drawing 619.x |  | Visual | 1 per Day /Installation |  | ²
Section 620: Pavement Marking
620 |  | Material | Marking Materials | All marking per MUTCD |  | Sec 1048 |  |  | Certification/ QPL | 1 per shipment | 1 per project |  | ²
620 |  | Construction | Permanent Marking | See Checklist |  | See Standard Drawing 620.x |  |  | Visual / Measurement | 1 per Installation |  | ²
620 |  | Construction | Temporary Marking | See Checklist |  | Sec 409, 413, Standard Drawing 620.x |  |  | Visual / measurement | 1 per Installation |  | ²
Section 621: Flowable Backfill
621 | .2.1, .2.2 | Materials | misc. components | Per 1005, 1018, 1019, 1054, 1070 |  |  |  |  | Qualified List - testing | 1 per Day /Activity | 1 per project |  | ²
621 | .3.1 | Materials | Mixture | Strength and consistency |  |  |  |  | Testing | 1 per Day /Activity | 1 per project |  | ²
621 | .4.1 | Construction | Flowable Fill | See Checklist |  |  |  |  | Visual | 1 per Day /Activity |  | ²
Section 622: Pavement and Bridge Surface Removal and Texturing
622 | 0.2 | Construction | Cold milling | See Checklist |  | See Sec 620 |  |  | Visual/ measurement | 1 per Day /Activity |  | ²
622 | 0.2 | Construction | Diamond Grinding | See Checklist |  | See Sec 502 |  |  | Visual/ measurement | 1 per Day /Activity |  | ²
Section 623: Concrete Bonding Compound, Epoxy Mortar and Epoxy Polymer Concrete Overlay
623 | .10.3.1 | Construction | Bonded Concrete, polymer concrete and Epoxy Mortar | See Checklist |  |  |  |  | Visual / Measurement | 1 per Day /Activity |  | ²
623 | .30.2 | Material | Epoxy | Sec 1039 |  |  |  |  | Certification/ QPL | 1 per Installation | 1 per project |  | ²
623 | .20.2 | Materials For epoxy mortar | Sand and aggregates | Section 1039 |  |  |  |  | Certification/ QPL | 1 per Installation | 1 per project |  | ²
623 | .20.3.1 | Construction | Epoxy Polymer Overlay | See Checklist |  |  |  |  | Visual / Measurement | 1 per Day /Activity |  | ²
Section 624: Geotextile Construction
624 | 0.2 | Material | Geotextile | spec 1011 |  | AASHTO M288 |  |  | Certification | 1 per Product | 1 per Product |  | ²
624 | 0.3 | Construction Requirements | Geotextile | See checklist |  |  |  | plans | visual | 1 per Installation |  | ²
Section 625: Slab Stabilization
625 |  | Construction | Slab Undersealing and Jacking | See Checklist |  | TM64, Sec 501 |  |  | Visual/ measurement | 1 per Installation |  | ²
625 |  | Material | Polyurethane, asphalt, cement, flyash, grout |  |  | 1015, 1018, 1019, 1066, 1070 |  |  | certification | 1 per Installation | 1 per project |  | ²
Section 626: Rumble Stripes
626 | 0.2 | Construction | Rumble Stripes | see Checklist |  |  | disposal Sec 622 |  | Visual/ measurement | 1 per 1000' |  | ²
Section 627: Contractor Surveying and Staking
627 | 0.2 | Contractor Surveying and Staking | Construction | See Checklist |  |  |  |  | visual | 1 per Installation |  | ²

## 700
DIVISION 700: Structures | [9 empty] | Minimum Frequency |  | QC Documents
[10 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  |  | Acceptance Criteria
Section 701: Drilled Shafts
701 | 2 | Preconstruction Submittals |  | See Checklist |  |  | Submitted 30 days in advance |  | Documentation | 1 per Structure |  | ²
701 | 0.3 | Material | Mix Components - Aggregates and Cementitous | Per Sec 1036, 1054, 1055. Concrete Aggregates, Cementitious Materials |  |  |  |  | test | See 501 | See 501 |  | ²
702 | .2.1 | Material | Rebar and Mix Components - PAL | see Sec 501 |  |  |  |  | PAL | 1 per Shipment | 1 per Shipment |  | ²
701 | 0.3 | Material | Mortars, Grouts, and Water | Per Sec 1066 and 1070 |  |  |  |  | Certification | 1 per Shipment | 1 per project |  | ²
701 | .3.1 | Concrete mixture | Air, Slump, Cylinders | Use B2, see Sec 501 |  |  |  |  | testing | 1 per 100 CY/pour/day | 1 per 500 CY |  | ²
701 | .3.2 | Material | Casing | [5 empty] | Manufacturers Certification and Mill Reports | 1 per Shipment | 1 per project |  | ²
701 | .3.2.. | Casing | Condition and Properly Sized | See Checklist |  |  |  |  | Visual / Measurement | 1 per shaft |  | ²
701 | .3.2.6 | Casing | Welding Procedures | Sec 1080 |  |  |  |  | documentation | 1 per each | 1 per project | ²
701 | .3.3.3 | Slurry | Approval, Preparation, control tests, and sampling | See Checklist |  |  | Preapproval for slurry. |  | Visual / Documentation | 1 per structure |  | ²
701 | 0.4 | Construction | Sequence, Methods, Time Limitations | See Checklist |  |  |  |  | Visual/ Measurement | 1 per Each Shaft |  | ²
701 | .4.10.3 | Excavation Inspection | Television Camera Inspection | See Checklist |  |  |  |  | Visual / Documentation | 1 per Each Shaft |  | ²
701 | .4.1.1. | Excavation Inspection | Rock Socket Foundation Inspection | See Checklist |  |  |  |  | Visual / Documentation | 1 per Each Shaft |  | ²
701 | .4.11.1 | Log and Cores of Excavated Material | For shale, sand, or siltstone | See Checklist |  |  |  |  | Documentation | 1 per Each Shaft |  | ²
701 | .4.12 | Reinforcing Cage and Spacers | Fabrication and Placement | See Checklist |  |  |  |  | Visual | 1 per Each Shaft |  | ²
701 | .4.13.1 | Concrete Placement | General Conditions | See Checklist |  |  |  |  | Visual / Measurement | 1 per Each Shaft |  | ²
701 | .4.1.7 | Integrity Inspection | Crosshole Sonic Log testing | See Checklist |  |  |  |  | document | 1 per Each Shaft |  | ²
701 | .4.17.1 | Integrity Inspection | Coring | See Checklist |  |  | Only when needed |  | Visual | 1 per each occurrence |  | ²
701 | 0.5 | Drilled Shaft Load Tests |  | If required by contract. |  |  |  |  | Visual / Measurement | 1 per each occurrence |  | ²
Section 702: Load Bearing Piles
702 | .2.1 | Material | Rebar | see Sec 1036 |  |  |  |  | PAL | 1 per Shipment | 1 per Shipment |  | ²
702 | .2.1 | Material | Mix Components - Aggregates and Cementitious | see Sec 501 |  |  | Aggregates, Cementitious Materials, Admixtures |  | Testing | See 501 | See 501 |  | ²
702 | .2.2 | Material | Piles and Tips | [5 empty] | Documentation | 1 per shipment | 1 per shipment |  | ²
702 | .2.2 | Concrete mixture | Air, Slump, Cylinders | see Sec 501 |  |  |  |  | testing | 1 per 100 CY/pour/day | 1 per 500 CY |  | ²
702 | .3.1 | Construction | Installation | See Checklist |  |  |  |  | Visual/ Measurement | 1 per Each Shaft |  | ²
702 | .4.2 | Construction | Equipment | See Checklist |  |  |  |  | Visual / Measurement | 1 per Pile |  | ²
Section 703: Concrete Masonry Construction
703 | .2.0, .2.1 | Material | Bearing Pads | Per Sec 1038 |  |  |  |  | Testing / Certification | 1 per Shipment | 1 per project |  | ²
703 | .2.0, .2.1 | Material | Rebar, Curing, and Sealing Compounds | see Sec 501, 1057, 1055, 1053, 1036 |  |  |  |  | PAL | 1 per Shipment | 1 per Shipment |  | ²
703 | .2.0, .2.1 | Material | Mix Components - Aggregates and Cementitous | see Sec 501 |  |  | Aggregates, Cementitious Materials, Admixtures |  | Testing | See 501 | See 501 |  | ²
703 | .3.1 | Concrete mixture | Air, Slump, Cylinders | see Sec 501 |  |  |  |  | testing | 1 per 100 CY/pour/day | 1 per 500 CY |  | ²
703 | .3.1 | Construction | Forms, Placement, Finishing | See Checklist |  |  |  |  | Visual | 1 per pour |  | ²
703 | .3.1 | Construction | Curing or Sealing | See Checklist |  |  |  |  | Visual / measurement | 1 per pour |  | ²
703 | .3.4, .3.4.1 | Construction | Joint Placement | See Checklist |  |  |  |  | Visual | 1 per pour |  | ²
703 | .3.6.1.5 | Opening to Traffic | Construction or Public | See Checklist |  |  |  |  | Documentation | 1 per activity |  | ²
703 | .3.9 | Construction | Temperature Control and Limitations | See Checklist |  |  |  |  | Measurement | 1 per pour |  | ²
703 | .3.1.1 | Extending/ Widening Structures | surface condition | See Checklist |  |  |  |  | Visual | 1 per pour |  | ²
703 | .3.1.1 | Stenciling ID Numbers |  | See checklist |  |  |  |  | Visual | 1 per structure |  | ²
Section 704: Concrete Masonry Repair
704 | .2. | Material | Rebar, Curing, and Sealing Compounds | see Sec 501, 1057, 1055, 1053, 1036 |  |  |  |  | PAL | 1 per Shipment | 1 per Shipment |  | ²
704 | .2. | Material | Mix Components - Aggregates and Cementitous | see Sec 501 |  |  | Aggregates, Cementitious Materials, Admixtures |  | Testing | See 501 | See 501 |  | ²
704 | .2. | Material | Bearing Pads, Epoxies, Water | Sec 623, Sec 1039, Sec 1070 |  |  |  |  | documentation | 1 per shipment | 1 per shipment |  | ²
704 | .2. | Material | Curing | Liquid Membrane per Sec 1055 or water |  |  |  |  | PAL / Visual | 1 per shipment | 1 per shipment |  | ²
| .2. | Material | Special Motar | [5 empty] | QPL | 1 per shipment | 1 per shipment |  | ²
704 | .2. | Concrete mixture | Air, Slump, Cylinders | see Sec 501 |  |  |  |  | testing | 1 per pour/day | 1 per 500 CY |  | ²
704 |  | Construction | Superstructure Repairs | See Checklist |  |  | If Concrete See 501 |  | Testing | 1 per Activity, 1 per Day min |  | ²
704 |  | Construction | Substructure Repair | See Checklist |  |  | If Concrete See 501 |  | Testing | 1 per Activity, 1 per Day min |  | ²
704 |  | Construction | Epoxy Sealing | See Checklist |  |  |  |  | Visual | 1 per Activity, 1 per Day min |  | ²
Section 705: Prestress Members
705 | .2. | Material | Prestressed Concrete Members | Per Sec 1029 |  | Girders should be stamped and reported by MoDOT inspector at plant or otherwise released |  |  | Documents | 1 per Activity or Shipment | 1 per Structure |  | ²
705 | .4. | Construction | Handling and Erection | See Checklist |  |  |  |  | Visual | 1 per Activity, 1 per Day min |  | ²
Section 706: Reinforcing Steel for Concrete Structures
706 | .2.1, .2.2 | Material | Reinforcing Steel and splices | Per Sec 1036 |  |  |  |  | PAL | 1 per Shipment | 1 per project |  | ²
706 | .2.1, .2.2 | Material | Foreign Reinforcing Steel | Per Sec 1036 | To accept foreign steel, additional accounting is required |  |  |  | Documentation | 1 per Shipment | 1 per project |  | ²
706 | .3.1 | Construction Requirements | Verification, Handling and Storage of Reinforcing Steel | See Checklist |  |  | Incoming PAL material should be inspected for disposition remarks |  | Visual | 1 per shipment |  | ²
Section 707: Conduit System on Structures
707 | 0.2 | Conduit System on Structure | Material | Per Sec 1060 & 1062 |  |  |  |  | Certification | 1 per Shipment | 1 per project |  | ²
707 | .3.1 | Construction | Conduit Systems | See Checklist |  |  |  |  | Visual | 1 per Structure |  | ²
Section 710: Epoxy Coated Reinforcing Steel
710 | .2.1 | Material | Epoxy Reinforcing Steel and splices | Per Sec 1036 |  |  |  |  | PAL | 1 per Shipment | 1 per project |  | ²
710 | .2.2 | Material | Foreign Reinforcing Steel | Per Sec 1036 | To accept foreign steel, additional accounting is required |  |  |  | Documentation | 1 per Shipment | 1 per project |  | ²
710 |  | Material | Field Epoxy Repair Material | Repair Material should be as recommended by the epoxy coater |  |  |  |  | Documentation | 1 per Activity | 1 per project |  | ²
710 | .3.1 | Construction Requirements | Verification, Handling and Storage of Epoxy Rebar | See Checklist |  |  | Incoming PAL material should be inspected for disposition remarks |  | Visual | 1 per shipment |  | ²
Section 711: Protective Coatings for Exposed Concrete Surfaces
711 | .2. | Material |  | Per Sec 1059 |  |  |  |  | QPL / Certification | 1 per Shipment | 1 per project |  | ²
711 | .3.1 | Construction | Protective Coatings | See Checklist |  |  | Random dry film thickness |  | Visual / Measurement | 1 per structure |  | ²
Section 712: Structural Steel Construction
712 | .2. | Material | Misc Structural Steel | Per Sec 1037, 1038, 1045, 1066, 1081 |  |  |  |  | Documentation | 1 per Shipment | 1 per project |  | ²
712 | .2. | Material | Nuts, Bolts, and Washers | Per Sec 1080 |  |  |  |  | PAL | 1 per Shipment | 1 per project |  | ²
712 | .5.1 | Structural Steel Construction | Erection, Bolt Tightening, Finishing | See Checklists |  |  |  |  | Visual / Testing | 1 per Activity, 1 per Day min |  | ²
712 | .5.1 | Construction | Field Welding | See Sec 1080 |  | Welder qualifications on file. Contractor developed Checklist based off contract documents. |  |  | Documentation | 1 per Structure |  | ²
Section 713: Thrie Beam for Bridge Guardrail
713 | .2. | Material | Thrie Beam; Bridge Guardrail | Per Sec 1040 |  |  |  |  | documentation | 1 per Shipment | 1 per project |  | ²
713 | .3. | Construction Requirements | Thrie Beam; Bridge Guardrail | See Checklist |  |  |  |  | Visual | 1 per Activity, 1 per Day min |  | ²
Section 715: Vertical Drain at End Bents
715 | .2. | Material | Vertical Drain | See Sec 1000, Sec 1011, 1012, 1013, & 1022 |  |  |  |  | Certification | 1 per Shipment | 1 per project |  | ²
715 | .3.1 | Construction Requirements | Vertical Drain | See Checklist |  |  |  |  | Visual | 1 per Activity |  | ²
Section 716: Neoprene Bearings
716 | .10.2 | Neoprene Bearings | Material | Per Sec 1038 |  | Check dimensions per plan |  |  | documentation | 1 per Shipment | 1 per project |  | ²
Section 717: Neoprene and Silicone Joint Systems
717 | .10.2 | Material | Neoprene Glands | Per Sec 1073 |  | Check dimensions per plan |  |  | PAL | 1 per Shipment | 1 per project |  | ²
717 | .20.2 | Material | Steel nosing |  |  | Check dimensions per plan |  |  | measurement | 1 per Activity, 1 per Day min | 1 per project |  | ²
717 | .30.2 | Neoprene and Silicone | Silicone Expansion Joint Sealant | Per Sec 1057 |  |  |  |  | PAL | 1 per Activity, 1 per Day min | 1 per project |  | ²
717 | .30.3 | Construction Requirements | Joint Systems | See Checklist |  |  | Barrier wall joint checklist rate: 1 per structure |  | Visual | 1 per Joint |  | ²
Section 720: MSE Wall Systems
720 | .2., .2.5. | Material | Concrete Mixtures | see Sec 501 |  |  | Class B or B1. Air entrainment for coping |  | testing | 1 per 100 CY/pour/day | 1 per 500 CY |  | ²
720 | 0.2 | Material | Select Granular Backfill | Per 1010, Resistivity (if metal straps). |  |  |  |  | Testing / Certification | 1 per product | 1 per project |  | ²
720 | 0.2 | Material | Geotextile, Drainage Materials, Anchors, Components | Per 1010, 1011, 1013, 1039 |  |  |  |  | Certification | 1 per Shipment | 1 per project |  | ²
720 | .2.1, .2.2 | Material | Reinforcement Steel | Epoxy coated if panel within 10' of roadway, Per Plan |  |  | Sec 1036 |  | PAL | 1 per Shipment | 1 per project |  | ²
720 | .2.4 | Material | Unit Fill Small Block Walls | Gradation D or E from Sec 1005, T27 |  |  |  |  | Testing | 1 per product | 1 per project |  | ²
720 | .4.1.1 | Construction | Wall Systems | See Checklist |  |  |  |  | Measurement | 1 per day |  | ²
720 | .4.2.2 | Material | Precast Panels and Coping | Sec 1052 |  | May be stamped by District Materials |  |  | Visual / Measurement | 1 per shipment | 1 per project |  | ²
Section 724: Pipe Culverts
724 | .2.2 - .2.3 | Construction | Installation of all types | See Checklist |  |  |  |  | visual / testing | 1 per location | 1 per project | ²
724 | .2.3 | Construction | Post Installation Performance Inspection | See Checklist |  |  |  |  | testing | 1 per location | 1 per project | ²
Section 725: Metal Pipe and Pipe Arch Culverts
725 | .1., .2. | Materials | Metal Pipe and Pipe Arches | Division 1000, Materials details 1020, 1021, 1024, 1027 |  |  |  |  | Pipe Program | 1 per Shipment | 1 per project |  | ²
725 | .3.1 | Construction | Repairs |  |  | See Checklist |  |  | Visual | 1 per location |  | ²
725 | .3.1 | Construction | Installation | See Sec 724 |  | See Checklist |  |  | Visual, Level, Measurement | 1 per Installation |  | ²
725 | .3.2.1 | Material | Soil Conditions | Testing of soil to allow choice of metal |  |  |  |  | testing | 1 per project | 1 per project |  | ²
Section 726: Rigid Pipe Culverts
726 | .1.1, .2. | Materials | Concrete and Clay Pipes and Pipe Arches and Joint Materials | Division 1000, Material details 1026, 1030, 1034, 1035, 1057, 1066 |  |  |  |  | Pipe Program | 1 per Shipment | 1 per project |  | ²
726 | .3.1 | Construction | Installation | See Sec 724 |  | See Checklist |  |  | Visual, Level, Measurement | 1 per Installation |  | ²
Section 727: Structural Plate Pipe and Plate Pipe-Arch Culverts
727 | .1., .2. | Materials | Structural Plate Pipe and Structural; Plate Pipe-Arch Culverts |  | Division 1000, Materials Details, Sec. 1023 and 1024 |  |  |  | Certification | 1 per Shipment | 1 per project |  | ²
727 | .3.1 | Construction | Installation |  |  | Contractor developed Checklist based off contract documents. |  |  | Visual / Measurement | 1 per Pipe |  | ²
Section 730: Thermoplastic Pipe Culverts
730 | .2. | Material | Thermoplastics | Sec 1020, 1032, 1047, 1041, 1028 |  |  |  |  | Pipe Program | 1 per Shipment | 1 per project |  | ²
730 | .3.1 | Construction | Installation | See Sec 724 |  | See Checklist |  |  | Visual, Level, Measurement | 1 per Installation |  | ²
Section 731: Precast Reinforced Concrete Manholes and Drop Inlets
731 | .2.1 | Materials | Precast Manholes and Drop Inlets | Per plans, May be stamped by district. |  | Sec 1033, 1055, 1057,1066 |  |  | Visual / Measurement | 1 per shipment | 1 per project |  | ²
731 | .2.2 | Materials | Footing Concrete | Sec 501 |  |  | Air entrainment not required |  | Visual / Measurement | 1 per shipment | 1 per project |  | ²
731 | .3.1 | Construction | Installation and backfilling | See Checklist |  |  |  |  | visual / testing | 1 per day |  | ²
Section 732: Flared End Section
732 | .2. | Material | precast concrete or metal flared end sections | Sec 1020, 1032, 1057, 1066 |  |  |  |  | Visual / Measurement | 1 per Shipment | 1 per project |  | ²
732 | .2.2 | Materials | Cast in place Concrete | Cast-in-place toe walls constructed of Class B, B-1 per section 501 |  |  | Air entrainment not required. Cured per Sec 703 |  | Testing | 1 per 100 CY/pour/day | 1 per project |  | ²
732 | .3.1 | Construction | installation | See Checklist |  |  |  |  | Visual | 1 per day |  | ²
Section 733: Precast Concrete Box Culverts
733 | .2. | Material | Misc | Per plans, May be stamped by district. |  |  | sec 1049, 1057, 1066 |  | Visual / Measurement | 1 per Shipment | 1 per project |  | ²
733 | .3.1 | Construction | Installation and backfilling | See Checklist |  |  |  |  | visual / testing | 1 per day |  | ²
Section 734: Installation of Pipe by Horizontal Boring Methods
734 | .2. | Material | misc. | Division 1000 Materials details |  |  |  | 1026, 1075 | documentation | 1 per Shipment | 1 per project |  | ²
734 | .3.2. | Construction requirements | misc. | Contractor developed Checklist based off contract documents. |  |  |  |  | Visual | 1 per structure |  | ²
Section 735: Culvert Lining
735 | .2., .2.1 | Material | Metal Pipe Liners | Division 1000 Materials details. 1046 |  |  |  |  | Documentation | 1 per Shipment | 1 per project |  | ²
735 | .2., .2.1 | Material | Plastic Pipe Liners | Division 1000 Materials details. 1046 |  |  |  |  | QPL | 1 per Shipment | 1 per project |  | ²
735 | .2., .2.1 | Material | Grout | , 1066 |  |  |  |  | Documentation | 1 per Shipment | 1 per project |  | ²
735 | .3. | Construction | Installation | See Checklist |  |  |  |  | visual / measurement | 1 per Pipe Liner |  | ²

## 800
DIVISION 800: Roadside Development | [7 empty] | Minimum Frequency |  | QC Documents
[8 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  | Acceptance Criteria
Section 801: Lime and Fertilizer
801 | .2 | Materials | Lime & Fertilize | Rates in JSP. Effective Neutralizing Materials (ENM) used for lime quantities |  |  | Certification or Label Analysis | 1 per Shipment | 1 per Project |  | ²
801 | .4 | Construction Requirements | Line and Fertilizer | See Checklist |  |  | Measurement | 1 per Activity |  | ²
Section 802: Mulching
802 | .2 | Materials | Vegetative Mulch and Mulch Overspray (Spec Book) |  |  |  | Certification / Visual | 1 per Shipment | 1 per Project |  | ²
802 | .3 | Construction Requirements | Mulch Application | See Checklist | Apply within 24 hours of seeding |  | Measurement | 1 per Activity |  | ²
802 | .3 | Construction Requirements | Overspray Application | See Checklist |  |  | Measurement | 1 per Activity |  | ²
Section 803: Sodding
803 | .2 | Materials | Sodding | As stated on plans |  |  | Certification | 1 per Shipment | 1 per Project |  | ²
803 | .3 | Sodding | Construction | See Checklist |  |  | visual | 1 per Activity |  | ²
Section 804: Topsoil
804 | .2 | Construction Requirements | Topsoil | Source Approved by Engineer | Free of Objectionable Material |  | Visual / Measurement | 1 per Activity |  | ²
Section 805: Seeding
805 | .2 | Material | Seed | Table of purity and germination requirements |  | Mixture per contract requirements | Certification | 1 per Shipment | 1 per Project |  | ²
805 | .3.1 | Construction | Seed Application | See Sec 801 | See Checklist |  | Visual / Measurement | 1 per Activity |  | ²
805 | .4 | Construction | Growth Acceptance | See Checklist |  | Activity is an "representative area" | visual | 2 per Activity |  | ²
Section 806: Pollution, Erosion and Sediment Control
806 | .90 | Materials | Temporary Erosion Control Blanket (Spec Book) | Installation per Manufacturers recommendations |  | Material certification per sec 1011 | Certification / Visual | 1 per Installation | 1 per Project |  | ²
806 | .4 | Construction Installation | Poll, Erosion, Sediment Control | Current SWPP, EPG, and applicable permits |  | See Checklist | Visual | 1 per activity |  | ²
806 | .4 | Construction Maintenance | Poll, Erosion, Sediment Control | Current SWPP, EPG, and applicable permits |  | Erosion Control Inspection Form | Visual | 1 per Week/ Rainfall Event | 1 per Week/ Rainfall Event |  |  | ²
806 | .90 | Temporary Materials | Erosion Control Blanket, Pipe, Seeding, Mulching | Per plans |  | Material certification per sec 1011 | Certification / Visual | 1 per Installation | 1 per Project |  | ²
Section 808: Trees, Shrubs, and Other Plants
808 | .2 | Materials | Plant Material | Certified free of insects and disease | Mo Dept. of Agriculture |  | Certificate / Measurement | 1 per Shipment | 1 per Project |  | ²
808 | .3 | Construction requirements | Planting and Maintenance | See Checklist |  |  | Visual | 1 per Activity |  | ²

## 900
DIVISION 900: Traffic Control Facilities | [7 empty] | Minimum Frequency |  | QC Documents
[8 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | Electronic Process | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  | Acceptance Criteria
Section 901: Highway Lighting
901 | 0.3 | Materials | Misc Lighting material | Table of all components and their Sec 1000 spec reference, Sec 1091, Sec 1080, Sec 1066 |  | Meet appropriate AASHTO or ASTM | certification | 1 per Shipment | 1 per project |  | ²
901 | 0.3 | Materials | Galvanizing | Check coating weight |  | Sec 1081 | Testing | 1 per Shipment | 1 per project |  | ²
901 | .3.1 | Materials | Approval of components and DEC | before construction, a listing of all materials should be submitted to the Engineer for approval. |  | District Engineers Certification D-15 | certification | 1 per project | 1 per project |  |  | ²
901 | .3.2 | Materials | Concrete | Per Plan and Sec 501 |  | Test first load | visual / test | 1 per day | 1 per 500 CY |  | ²
901 | .3.2 | Materials | Reinforcing Steel and hardware | See Sec 1036, 1080 |  |  | PAL | 1 per shipment | 1 per project |  | ²
901 | 0.4 | Construction | Misc Lighting | See Checklist | Test Period for performance |  | visual | 1 per circuit |  | ²
Section 902: Traffic Signals
902 |  | Materials | Misc Signal material | Table of all components and their Sec 1000 spec reference, Sec 1092, Sec 1080, Sec 1066 |  | Meet appropriate AASHTO or ASTM | certification | 1 per Shipment | 1 per project |  | ²
902 |  | Materials | Galvanizing | Check coating weight |  | Sec 1081 | Testing | 1 per Shipment | 1 per project |  | ²
902 |  | Materials | Approval of components and DEC | before construction, a listing of all materials should be submitted to the Engineer for approval. |  | District Engineers Certification D-15 | certification | 1 per project | 1 per project |  |  | ²
902 |  | Materials | Concrete | Per Plan and Sec 501 |  | Test first load | visual / test | 1 per day | 1 per 500 CY |  | ²
902 |  | Materials | Reinforcing Steel and hardware | See Sec 1036, 1080 |  |  | PAL | 1 per shipment | 1 per project |  | ²
902 | .4.5 | Construction | Misc Signal material | See Checklist | Test Period for performance |  | visual | 1 per circuit |  | ²
Section 903: Highway Signing
903 | .2., .2.1 | Material | Misc Signing Materials | Table of all components and their Sec 1000 spec reference, Sec 1042, Sec 1080, Sec 1066 |  | Table for ASTM, AASHTO requirements | documentation | 1 per Shipment | 1 per project |  | ²
|  | Material | Tubular Supports |  |  |  | Testing | 1 per support | 1 per project
903 | .2., .2.1 | Material | Overhead Sign Trusses | Fabrication inspection by Bridge |  |  | testing | 1 per truss | 1 per shipment |  | ²
903 | .2., .2.1 | Materials | Galvanizing | Check coating weight |  | Sec 1081 | Testing | 1 per Shipment | 1 per project |  | ²
903 | .2.3 | Materials | Reinforcing Steel and hardware | See Sec 1036, 1080 |  |  | PAL | 1 per Shipment | Verify documentation |  | ²
903 | .2.4 | Materials | Concrete | Per Plan and Sec 501 |  | Test first load | visual / test | 1 per day | 1 per 500 CY |  | ²
903 | .2.5 | Construction | Roadside Signs | See Checklist | PSST, Pipe, and Structural Posts |  | visual / Measurement | 1 per day |  | ²
903 | .2.5 | Construction | Overhead Signs | See Checklist | Tubular supports and truss supports |  | visual / Measurement | 1 per structure |  | ²

## JSP ITS
JSP | Intelligent Traffic System
|  | I.T.S. | Dynamic Message Sign Footing | Class B, Sec 501, 703 | Sec. 706, 712 | lab report | 1 per 50yds | (1) per 500 CY |  | ² | ²
|  | I.T.S. | CCTV Foundation | Class B, Sec 501, 703 | Sec. 706, 712 | lab report | 1 per 50yds | (1) per 500 CY |  | ² | ²
|  | I.T.S. | Drilled Shafts for CCTV & DMS Structures | Sec 701 except 701.4.10.3 thru 701.4.11.4, 701.6.4, 701.6.5, 701.7.5 & 701.7.6 |  | visual | Per Foundation | Verify completion |  | ²
|  | I.T.S. | DMS Sign Structure | AWS D1.2 | ASTM's for sign posts | certificate of compliance/mill Test Reports | Per Shipment | Verify certification |  | ² | ²
|  | I.T.S. | Conduit Systems | Type of system as shown on plans | Submit shop drawing detail for support system | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Conduit Systems | Orange for Communication, Black for Power, Meet Spec. 1060 | Install tracer wire, pull rope, marking tape | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Conduit Systems | 10% of slurry mix shall be of a high grade Bentinite |  | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Conduit Systems | Fill void between drilled hole and conduit | Backfill exposed area to grade | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Fiber Optic Cable | As shown on plans | Spec 1092 | certificate of compliance | Per Completed Fiber run between Cabinets | Verify certification | ² | ² | ²
|  | I.T.S. | Fiber Optic Cable | Access cable of 20' in intermediate pb, 30' at cabinet | Label cable, fill used conduits to prevent water entry | visual | Per Completed Fiber run between Cabinets | Verfiy completion |  | ²
|  | I.T.S. | Fiber Optic Cable | Secure splices, separate tray for each buffer tube | Fusion splice w/ LID or HDCM system | visual | Per Completed Fiber run between Cabinets | Verify completion |  | ²
|  | I.T.S. | Fiber Optic Cable Acceptance Testing | Test Result Documentation |  | report | Per Completed Fiber run between Cabinets | Verify test data |  | ² | ²
|  | I.T.S. | Equipment Cabinets | As shown on plans |  | certificate of compliance | Per Completed Fiber run between Cabinets | Verify certification |  | ²
|  | I.T.S. | CAT 5E Cable | As shown on plans |  | certificate of compliance | Per Completed Fiber run between Cabinets | Verify certification |  | ²
|  | I.T.S. | Communication Equipment | As shown on plans |  | certificate of compliance/visual | Per Completed Fiber run between Cabinets | Verify certification |  | ²
|  | I.T.S. | DMS Assembly | As shown on plans |  | certificate of compliance/visual | Per DMS Structure | Verify certification |  | ²
|  | I.T.S. | CCTV Camera Assembly | As shown on plans |  | certificate of compliance/visual | Per CCTV Structure | Verify certification |  | ²