QRG - SiteManager/Estimate Based Documentation Records

The term "Documentation Record" is used extensively in this QRG because "Documentation Record" or "Doc Record" is the traditional terminology; however, the net effect of this QRG is to make the traditional Documentation Record obsolete.

Documentation Records cover a variety of issues related to any given contract.  It is the Resident Engineer's responsibility to see that documentation record issues are diligently recorded in the appropriate location of SiteManager and that the appearance of this information in the Estimate is adequate and appropriate to the intent.  In most instances this will require that the Resident Engineer perform a review, or designate a person to review this detail of the estimate prior to sending it to the contractor.

Documentation records are intended to be information on work performed on a project that cannot be easily seen or measured after the work is complete.  Two common examples of work are erosion control and temporary signing, both of which are done on parts of a typical job, for some finite period of time, and evidence of the work is gone or nearly absent from the final project.  Documentation records may be needed in other situations, such as providing information on contractor payments where calculations are necessary to make the payment determination.

There are two primary reasons for the information traditionally called Documentation Record.

1) 	A detailed record of the work, as historical proof that the work was performed

2)	 Information the contractor may review in a timely fashion and use to confirm or dispute quantities, locations of work, calculations, logic behind calculations, or other routine activities where a controversy may result later in the job's life.

The documentation record process described in this QRG does not change the fact that other information may need to be communicated to the contractor verbally, by e-mail, in a letter on MoDOT letterhead, by Order Record, by Change Order, or by other applicable means.

The following list includes some examples of issues and activities that need to be well documented.  The list should not be considered complete.  Any issue or activity that meets the criteria listed above should be documented in SiteManager and have that information included in the Estimate report by including the information in the appropriate area of SiteManager.

# EXAMPLES OF ISSUES AND ACTIVITIES THAT NEED DOCUMENTATION:

## 1)  Estimate Data Type: Contract Adjustment

- Asphalt Cement Price Adjustments (Indexing - Include detailed calculations for any that are not automatically performed)

- Asphalt Pavement Price Adjustments (QC/QA results affecting pay - Include detailed calculations and information related to adjustment)

- Fuel Price Adjustments (Indexing - Include detailed calculations for any that are not automatically performed)

- Pavement Smoothness Price Adjustments (Include detailed calculations and information related to adjustment)

- Surveying Supplies (When contractor does not provide, or advised MoDOT to obtain and bill to contract, include details of the invoice and circumstances)

Contract Adjustment entries should provide enough detail so the typical reader has no questions regarding the adjustment.

## 2)  Estimate Data Type: Line Item Adjustment

- Concrete Pavement Price Adjustments (QC/QA results affecting pay - Include detailed calculations and information related to adjustment)

- Manual Fuel Adjustments (Indexing - especially instances where quantities are adjusted later, precipitating a need to adjust indexing)

Line Item Adjustments should provide enough detail so the typical reader has no questions regarding the adjustment.

## 3)  Estimate Data Type: Line Item Payment

- Any  Pay Item 	(Include location, amount and date of installation.  If special details are required include them in the remarks for that Location Sequence Number

- Compacting In Cut (one area of work may be done before another area.  Each completed area should be documented as completion is achieved.)

- Modified Cold Milling (one area of work may be done before another area.  Each completed area should be documented as completion is achieved.)

- Undergrading (one area of work may be done before another area.  Each completed area should be documented as completion is achieved.)

Line Item Payment entries should provide enough detail so the typical reader has no questions regarding the payment or location of the work.

## 4)  Estimate Data Type: DWR Documentation Remark

- Slope Stake Marking Explanation

- Retroreflectometer readings taken by the Project Office

- Seedings/plantings details

A DWR Documentation Record Remark can be used to document anything that does not logically fit in one of the categories above.

# THE MECHANISM TO ACHIEVE PROPER DOCUMENTATION:

## 1A)  Estimate Data Type: Contract Adjustment

See other references to "Contract Adjustment" in the EPG, QRGs and SiteManager Policy and Procedure manual for additional details on Contract Adjustments.

Enter the Contract Adjustment in the Contract Adjustments window.  In the Remarks area, be certain to include calculations and details related to the issues such that the typical reader would have no questions regarding the work done, the reason for the payment, or the calculations performed to arrive at the payment or deduction.

The Estimate will reflect the entry above and this is considered adequate documentation of this payment.

## 2A)  Estimate Data Type: Line Item Adjustment

See other references to "Line Item Adjustment" in the EPG, QRGs and SiteManager Policy and Procedure manual for additional details on Line Item Adjustments.

Enter the Line Item Adjustment in the Line Item Adjustments window.  In the Remarks area be certain to include calculations and details related to the issues such that the typical reader would have no questions regarding the work done, the reason for the payment, or the calculations performed to arrive at the payment or deduction.

The Estimate will reflect the entry above and this is considered adequate documentation of this payment.

## 3A)  Estimate Data Type: Line Item Payment

See other references to "Daily Work Reports - Work Items entry" in the EPG, QRGs and SiteManager Policy and Procedure manual for additional details on Daily Work Reports - Work Items entries.

Enter the Work Items in the Daily Work Reports window, on the Work Items tab.

For each Work Item, provide an entry (Loc Seq Nbr) to document the quantity and location of the work.  The system requires either station or log mile.  Every feature, payment, or deduction applies to some point, some portion, or the entire job (job limits - generally you can ignore equations for this purpose).  This can be indicated via stationing (on a stationing job) or by Log Mile (on a Log Mile job).

When there are variations of width of work, skipped area, or other aspects that make a certain length of the work different from another, a new line should be added for that work (Loc Seq Nbr - click in the middle panel, then click New).  Certain features, such as detour signs, may be outside the project limits.  You may use TMS to determine the continuous Log Mile designation of the point, or you may reference the point from a stable landmark such as an intersection or a river.

Part of this information is listed in the Estimate, as in the example below.  This example covers the information above and below.  The balance of the information will be presented elsewhere in the Estimate, review the rest of the QRG, below.

If the description field and the location specific details do not provide enough information, a Remark specific to the Location Sequence Number can be added.

The remark will show up in the estimate subservient to the location information of the work.

There is one specialized template for Signs.  When your project has Construction Signs please use the template.  Navigate to Contract Item-DWR Template

Select your contract if it is not already selected and click Service Generate, or the Generate Button.  An error may display.  If so, click Continue.

Select the template from the Templates List and move it across to the Associated Templates by clicking the Add button.

Return to the DWR Window - Work Items Tab and enter a Loc Seq Nbr for your construction signs.

Click the DWR Template Icon:

This window will appear.  Select the Construction Signs Template by double clicking.

The following window should appear.  Fill in each sign that applies to the project.  The signs are selected from a list however, as it mentions in the instructions, a specialized sign can be added if necessary.  The area and total area are automatically calculated.

Either of the processes described above will result in the detail similar to the following.

## 4A)  Estimate Data Type: DWR Documentation Remark

See other references to "Daily Work Reports - Documentation Remarks" in the EPG, QRGs and SiteManager Policy and Procedure manual for additional details on Daily Work Reports - Documentation Remarks.

Enter any information of any type that needs "documentation record" information presented to the contractor.  Go to the DWR window and add a record of the type "Documentation Record".

The information will be provided in the estimate in the following format.

## Frequent Questions:

1)	Permanent signs:	Permanent Signs have multiple pay items each time a sign is installed (up to 6 individual items).  A contractor can easily drill and pour many sign footings in a day.  This can happen for several consecutive days on large projects.  Does each sign assembly need to be entered separately or could they be lumped together for sign payment?  Some sign locations have one sign and some have 10 or more.  In the past, we would add up the total for each pay item and make one entry.  It would also list the sign numbers being paid for but to get the station and offset you would need a set of plans to cross-reference.

SiteManager is the primary repository of information regarding the construction of a project.  While the signs are listed in the plans, SM needs to know when a particular sign was installed.  In order to know when the sign was installed we need to know which sign the record is addressing.  Note that we can come back to the job anytime and see a permanent sign.  While each individual sign must be referenced, the work done related to signs; footings, posts, etc. can be indicated as a single entry for each work item for the work you are paying that day.  The location would be project limits (or a subset of that, if you can determine it easily) and part of the description would be “placed according to the plans”.  This assumes that you have DWR remarks that indicate which signs (or sign components) were constructed on a given day.  This can be done as simply as possible, in most cases this would be via the unique number assigned to each permanent sign in the plans.  So… we need to know when and where the sign was placed, but the where can be a reference to the plans if the sign is placed according to the plans.

2)	Channel Post Delineators:  Can these be entered for a range?

Yes, “placed according to the plans”, then indicate the station or LM limits.  If there were exceptions, for example, the delineators were placed from LM 3.0 to LM 14.0 and LM 15.2 to LM 16.0; this would require two entries on Loc Seq Nbr line on the Work Items tab of the DWR.  Alternately, you could show LM 3.0 to LM 16.0 and put a Documentation Record remark type on the DWR Information tab and indicate the exception.  This kind of exception comment would make more sense for a few missing delineators, than it would for 1.2 miles of missing delineators.

3)	Construction Signs:  Several of these signs are portable mounted and will be used throughout the entire Project (i.e., Lane Drop package).

A recent project had a detour that detoured traffic up to 10 miles from the project.  What is the proper entry for the stations?  This detour had 68 sign locations with approximately 3 signs per location.  Many of these signs would be the same (i.e., 151, Detour, etc).  Would these need to be listed for each sign at each location or for each sign package?  Or could the total number of each sign be entered once?

There are special issues related to construction signs.  It is common that claims and lawsuits revolve around whether the signs are there, and which sign was where.  Each time you pay for construction signs you should indicate, literally, each of the signs and its specific location.  If it is a mobile sign, indicate its initial location and that it is “part of mobile signing package”.  This initial, explicit placement record should match standard placement of such signs in accordance with plans, specifications and MUTCD or other guide as may have been used.  This gives you an opportunity to establish that it is, in fact, a standard set of signs or that there are exceptions added or deleted.  Daily, in the DWR Remarks you would indicate that “the mobile signing described on <date> was in place in the appropriate position for today’s moving construction work and was in specification compliant condition.”

Extensive detours are rare; however, we may have more in the future.  We have established the precedent of providing excellent advisory signs.  It follows that our detours need to be complete and correct, and we need to document that fact.  If the motorist gets lost and it results in an injury, we could be liable if we could not prove that we signed properly.

4)	Ditch Checks:  Contractors often install several of these in a day, sometimes 30 to 40 or more.  If they are in the same area down a continuous ditch can a range be used or separate entry for each?

Individual checks should be indicated with a specific location.  A series of checks in a continuous ditch can be shown with beginning and ending station and the Description “<number> in accordance with plans and SWPP”. Note, in this instance a "continuous ditch" would encompass a series of checks placed in sequence as a group.  "Continuous ditch" should not typically be construed as running the full length of the project.

5)	Silt Fence:  See Ditch Checks

A single run of fence should be indicated with beginning and end.  A series of fences placed mostly continuous can be shown with beginning and ending station and the Description “in accordance with plans and SWPP”

6)	Type IV Obj Markers:  Current project they are not listed by station and offset.  These are quite often on roadway that is closed and may not have stationing on the plans.  Do we pick a station from plans best as possible?

Placement can be estimated if it is not designated on the plans.  In the Description field indicate, “placement estimated” but show the estimated stationing or LM designation

Bridge Items

7)	Piling, Pile Point Reinforcement, Girders, Bearing pads, Slab Drains:  Do these Items need to be reported individually or can we continue to report total length of pile for a bent,  Pile points for entire Bridge, Bearing pads, girders and Slab Drains when installed?

All of these are designated on the plans, including specific locations and quantity.  The location of placement would therefore be the limits of the structure (or the specific location would be acceptable, if easily determined.).

8)	Timely notification to the Contractor:  There may be instances when the contractor does work and we should document it and notify the contractor of the work even quicker than at the next estimate.  For example, work that is done and will be covered within a few days (paved over, backfilled, etc.).  What should we do then?

Make the normal entries in SiteManager, at least those related to the work in question.  Run an estimate and provide it to the contractor, and explicitly indicate that it is a preliminary estimate covering specifically that work that might be of special interest due to the contractor's progress.  Advise the contractor that he may wish to review those details and raise any concerns he may have while the area can still be visited and remeasured, retested, or whatever may be required.

9)	Retroreflectivity Details to the Contractor:  Should the retroreflectivety cover letter and spreadsheet results be provided to the contractor in the form of a documentation record?

If the contractor specifically requests to see the results, they may be provided in their native format (that is, no need to convert to some other format from the format provided by the consultant.  As long as the original data from the consultant is retained in the files, the raw data need not be entered into SiteManager in an attempt to produce it as part of the Estimate information process.

10)	Drop Inlets and other things that are the combination of multiple bid items:  Is it necessary to repeat all entries for each component of something like a drop inlet?  For example, a drop inlet will include excavation, the inlet (or components to cast-in-place), and grate and bearing plate.

Consider each Drop Inlet as an independent thing to be documented.  Provide great detail for the most important component (in this instance, the inlet).  If you install 5 drop inlets in one day, each of the 5 inlets needs to have its only line on the DWR Work Item tab, indicating its location and designation.  Work incidental to the drop inlet, such as excavation will need a single entry, with the work limits encompassing the placement of all 5 inlets, and a reference to the inlets that the excavation affected.  Same thing for grates and bearing plates, one entry for the day.  This process may be applied to other, similar processes, where the primary components get individual lines, and the incidental items get a single line per item, with a reference to the primary item.